DRAFT

Programme on Industrial Upgrading and Modernization in SADC Countries

March 2009

DRAFT

Programme on Industrial Upgrading and Modernization in SADC Countries

| Project Title: | Programme on Industrial Upgrading and Modernization in SADC Countries |
| --- | --- |
| Beneficiaries: | - Member States of the Southern African Development Community (SADC): Angola, Botswana, DR Congo, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, South Africa, Swaziland, Tanzania, Zambia and Zimbabwe - SADC Secretariat - The regional and national industrial support institutions in the SADC countries - The Ministries of Industry and Trade and SMEs - Industrial companies - Non-Governmental Organizations (NGOs) |
| Funding institution: | International Cooperating Partners (ICPs) |
| Implementing organization: | SADC |
| Executing organization: | SADC |

March 2009

# CONTENTS

LIST OF ABBREVIATIONS	7

EXECUTIVE SUMMARY	9

SECTION 1:	BACKGROUND AND SITUATION ANALYSIS	11

1.1	African Context	11

1.1.1	Background	11

1.1.2	Action Plan for the Accelerated Industrial Development of Africa	13

1.2	The SADC Context	14

1.2.1	Economic situation	14

1.2.2	Foreign Trade	17

1.3	Industrial sector analysis	20

1.3.1	General overview	20

1.3.2	Manufacturing Sector	22

1.3.3	Priority Sectors	26

1.3.4	Informal sector	33

1.4	Strengths and challenges of manufacturing sector	34

1.4.1	Advantages and opportunities	34

1.4.2	Weaknesses and challenges	35

1.5	Factor costs and competitiveness of manufacturing sector	37

1.6	Technical support institutions	40

1.7	EPA impact analyses	42

1.8	Financial mechanisms	43

1.8.1	Current situation in private sector financing	43

1.8.2	The Regional Industrial Development Fund	44

1.8.3	Schemes and mechanisms for funding upgrading and competitiveness	45

SECTION 2:	CONTEXT AND JUSTIFICATION OF THE PROGRAMME	47

2.1	SADC: Background, Strategy, Priorities and Challenges	47

2.1.1	SADC Regional Integration Process	47

2.1.2	Regional development strategies and objectives	48

2.1.3	SADC-EU EPA Negotiating Principles and Objectives	54

2.1.4	The major problems to be solved	55

2.2	Programme justification	55

2.2.1	The EPA Context	55

2.2.2	Lessons learned	56

2.3	UNIDO Initiative	57

2.4	Main beneficiaries of the Programme	58

2.5	Articulation of the Programme between regional and national levels	58

2.6	Complementary activities to Upgrading Programme	60

2.7	Coordination of potential donors	60

SECTION 3:	OBJECTIVES, COMPONENTS AND OUTPUTS OF THE PROGRAMME	61

3.1	Objectives	61

3.1.1	Global objective	61

3.1.2	Specific objectives	61

3.2	Programme components and outputs	61

SECTION 4:	APPROACH AND CRITERIA OF ELIGIBILITY TO THE PROGRAMME	67

4.1	UNIDO Approach	68

4.1.1	Upgrading and Restructuring	68

4.1.2	Upgrading technical support institutions	69

4.1.3	Strengthening economic information infrastructure (Strategic positioning studies)	71

4.1.4	Development of consortia and export promotion infrastructure	71

4.1.5	Promotion of partnership and industrial coaching	72

4.1.6	Establishment of traceability system	73

4.1.7	Supporting the informal sector SMEs	74

4.2	Criteria of eligibility to the Programme	75

4.2.1	Upgrading the formal sector SMEs	76

4.2.2	Financial restructuring	76

4.2.3	Assistance to informal sector SMEs	77

4.2.4	Examples of eligibility criteria applied in previous upgrading programmes	78

SECTION 5:	FUNDING AND BUDGET OF THE PROGRAMME	79

5.1	Funding of the Programme	79

5.1.1	Upgrading activities	79

5.1.2	Funding of upgrading activities	80

5.1.3	Average budget of the immaterial investments activities	81

5.1.4	Budget for group actions	83

5.1.5	Investment and operations budget estimates for Upgrading Offices:                   Case of Senegal	83

5.1.6	Proposed funding scheme	83

5.2	Budget of Upgrading and Modernization Programme	84

5.3	Detailed description of the budget	85

5.4	Expected impact of the Programme	87

SECTION 6:	MANAGEMENT AND COORDINATION OF THE PROGRAMME	91

6.1	Regional level	91

6.1.1	The SADC Secretariat	91

6.1.2	Regional Steering Committee	92

6.1.3	Technical Unit for Upgrading and Modernization	92

6.1.4	Technical assistance	93

6.2	National level	93

6.2.1	Member States	93

6.2.2	National Steering Committees	93

6.2.3	Offices for Upgrading and Modernization	93

6.3	Management, Monitoring and Evaluation of the Programme	95

6.3.1	Management of the Programme	95

6.3.2	Monitoring and Evaluation	95

6.3.3	Reporting	96

6.4	Assumptions and risks	96

6.5	Factors for success	97

# ANNEXES

# Terms of Reference for the Programme Formulation

# Logical Framework of the Programme

# Programme Activities by Outputs

# Programme Implementation Schedule

# Examples of Immaterial Investments Activities

# Examples of Technical Centers for Sectoral Support

# Country Reports

# Bodies and Persons Interviewed

# Scenarios for Indicative Budget of the Programme

LIST OF ABBREVIATIONS

| AB | Accreditation Body |
| --- | --- |
| ACP/EU | African Caribbean Pacific/European Union |
| ADB | African Development Bank |
| AFD | French Development Agency |
| AGOA | Africa Growth and Opportunity Act |
| APCI | African Productive Capacity Initiative |
| APSP | Association for the Promotion of the Private Sector |
| ARSO | African Regional Organisation of Standards |
| ASYCUDA | Automated System for Customs Data |
| AU | African Union |
| BDS | Business Development Services |
| CA | Conformity Assessment |
| CAB | Conformity Assessment Body |
| CAI | Conformity Assessment Infrastructure |
| CAP | Conformity Assessment Procedures |
| CDE | Center for the Development of Enterprise |
| CB | Certification Body |
| CEMAC | Economic and Monetary Community of Central Africa |
| COMESA | Common Market for East and Southern Africa |
| CSIR | Council for Scientific and Industrial Research |
| DANIDA | Danish International Development Agency |
| DFID | UK Department for International Development |
| DBSA | Development Bank of Southern Africa |
| ECA | Economic Commission for Africa |
| ECCAS | Economic Community of Central African States |
| ECOWAS | Economic Community of West African States |
| EIB | European Investment Bank |
| EPA | Economic Partnership Agreement |
| ESIPP | EU SADC Investment Promotion Programme |
| EU | European Union |
| FDI | Foreign Direct Investments |
| FTA | Free Trade Area |
| GCC | Global Commodity Chain |
| GHP | Good Hygiene Practice |
| GSP | Generalized System of Preference |
| GTZ | German Agency for Technical Cooperation |
| HACCP | Hazard Analysis and Critical Control Points |
| HIPC | Highly Indebted and Poor Countries |
| IB | Inspection Body |
| ICT | Information and Communication Technologies |
| IDC | Industrial Development Corporation |
| IDF | Industrial Development Forum |
| IFIs | International Financial Institutions |
| ILAC | International Laboratory Accreditation Cooperation |
| IMF | International Monetary Fund |
| IOC | Indian Ocean Commission |
| ISO | International Organisation for Standardisation |
| ITPO | Investment and Technology Promotion Offices |
| JCDCMAS | Joint Committee on Coordination of Assistance to Developing Countries in Metrology, Accreditation and Standardization |
| LDCs | Least Developed Countries |
| MCA | USAID Millennium Challenge Account |
| MDGs | Millennium Development Goals |
| MERCOSUR | Southern Common Market (Latin America) |
| MFIs | Micro-Finance Institutions |
| NEPAD | New Economic Partnership for African Development |
| NGO | Non-Governmental Organization |
| NIC | Newly Industrialized Country |
| NMI | National Metrology Institute |
| NSB | National Standards Body |
| NTBs | Non-Tariff Barriers |
| NTEs | Non-Traditional Exports |
| OECD | Organization for Economic Cooperation and Development |
| OIML | International Organization of Legal Metrology |
| PPP | Public Private Partnership |
| PRSP | Poverty Reduction Strategy Paper |
| PSDP | Private Sector Development Programme |
| QI | Quality Infrastructure |
| RATES | Regional Agriculture Trade Expansion Programme |
| RECs | Regional Economic Communities |
| RIDF | Regional Industrial Development Fund |
| RISDP | Regional Indicative Strategic Development Plan |
| SACA | Standards and Conformity Assessment |
| SACU | Southern African Customs Union |
| SADC | South African Development Community |
| SADC-DFRC | SADC Development Finance Resource Centre |
| SAGCH | Southern Africa Global Competitiveness Hub |
| SAPs | Structural Adjustment Programmes |
| SDS | Spatial Development Strategy |
| SMEs | Small and Medium Enterprises |
| SPS | Sanitary and Phytosanitary Measures (under WTO regulations) |
| TBT | Technical Barriers to Trade |
| TNCs | Transnational Corporations/Companies |
| UEMOA | West African Economic and Monetary Union |
| UNDP | United Nations Development Programme |
| UNIDO | United Nations Industrial Development Organisation |
| USAID | United States Agency for International Development |
| VAT | Value Added Tax |
| WB | World Bank |
| WTO | World Trade Organization |

EXECUTIVE SUMMARY

# In the Southern African Development Community (SADC) region, the industrial sector, in particular, small and medium-sized manufacturing enterprises play an increasingly important role in employment and wealth creation through value-addition and diversification of exports.

# However, in the context of globalization of the world economy and trade, a lack of productive capacities, supply-side constraints and low quality, as well as inadequate institutional and technical support infrastructure constitute the main constraints to SME development in SADC countries, and restricts their ability to take advantage of better access and integration into the global market.

# At the request of the SADC Secretariat, UNIDO has formulated the present Programme for Industrial Upgrading and Modernization in the SADC region.

# The objective of this programme is to contribute to the strengthening of industrial capacities in SADC countries to enable them to face the double-challenge of regional and world integration and improve competitiveness, thus supporting efforts of growth, employment creation, export promotion and poverty reduction.

Specifically, the Programme aims at generating the momentum for upgrading and improving the competitiveness of industries and related services. This will improve industrial competitiveness, growth by improving productivity and quality to enhance access to national, regional and international markets in the context of globalization and trade liberalization and economic diversification.

# The programme intervenes through the following two components:

- Support for upgrading and improving competitiveness of industries;

- Establishment/upgrading of the technical support institutions.

Current Programme proposal covers:

- Phase 1, the “start-up” or “pilot” phase of a 3-year period, which will kick-off the industrial upgrading and modernization activities at the regional and national levels for the pilot manufacturing enterprises and technical support institutions called to insure implementation and sustainability of the Programme.  This phase intends searching and developing the “success stories” through running some possible experiments.

- Phase 2, the “roll-out” phase of the Programme will draw on lessons learnt during Phase 1 and will be opened to all the remaining enterprises and support institutions, It will have a duration of 3 years with possible extension.

# This programme takes a multi-disciplinary approach involving SADC Secretariat, their Member States, technical support institutions, investment promotion agencies and export consortia to enhance capacities of both formal and informal priority sectors manufacturing enterprises. The approach is based on UNIDO’s previous experience in carrying out industrial upgrading and modernization programmes in Tunisia, Algeria and Senegal.

# On 31st March – 2nd April 2008, in Johannesburg, South Africa, the SADC Secretariat held the Regional Validation Workshop which approved the draft programme. The SADC Secretariat, delegates from Member States, representatives of private sector and UNIDO took part in this workshop.

- BACKGROUND AND SITUATION ANALYSIS

  - African Context

      - Background

Despite the liberalization of the world market, which offers significant opportunities for the advancement of trade and industry in Africa, most countries in the region have not been able to effectively benefit from trading opportunities in expanding markets in spite of emphasis in multilateral trade negotiations on the development dimension and some concessionary schemes available to African countries.

At present, Africa has one-sixth of the world’s population but a third of the world’s poor.  This fact is linked to the continent’s weak and deteriorating share of global trade and industrial output.  While the number of people living in absolute poverty in Africa has increased from 42% to nearly 50% within the past two decades, Africa’s share of world exports has fallen from 4.5% to 2.9%.  In terms of manufactured exports, Sub-Saharan Africa lags behind every other region – its share in world exports of manufactures is a mere 0.9%. Only in a few of the Sub-Saharan Africa countries the manufacturing value added/GDP ratio is above 20%. In a large number of African economies, the manufacturing sector’s contribution to GDP is less than 15% and in some cases lower than 5%.

Chart 1:

Africa’s share of world merchandise trade, 2005

Source: WTO International Trade Statistics, 2006

Chart 2:

Africa’s share in world exports of manufacturing goods, 2005

Source: WTO International Trade Statistics, 2006

The major reasons for Africa’s failure to benefit from these opportunities are largely linked to the lack of supply capacity needed to ensure necessary quantity and quality of products for export, technology gap and inability to demonstrate conformity of potential export products with international standards and the problems of integration into the multilateral trading system. The African economy is heavily dependent on the production and exports of primary products and the majority of African countries are yet to be involved in any significant sense in the medium- and high-technology segments of global manufacturing.

The greatest potential for economic and trade development of African countries lies in the manufacturing sector and in the transformation of African raw materials into semi-finished and finished products.  African enterprises need to develop regional value chains and link with global supply chains to market their products internationally.

The small and medium-sized enterprises, which predominate in African economies, have inherent difficulties with access to capital, productive capacity, technology and services because of resource limitations.  If these enterprises are to trade in global markets, they need to increase and upgrade their supply capacity, quality, competitiveness and conformity with importer-mandated product standards.  This involves both increased investment at the enterprise level and government support in improving productivity and technology extension services, training, export consortia and cluster development.  Clearly, in the present global setting the role of such trade support infrastructure becomes even more important.  It can provide support for building capacities to use new technologies, adapt and improve processes and products and move up the value chain into more sophisticated production activities.

      - Action Plan for the Accelerated Industrial Development of Africa

In response to these challenges and as a result of a series of sub-regional meetings held across the continent during 2002 and 2003, the African Ministers of Trade and Industry (CAMI) initiated the African Productive Capacity Initiative (APCI) to define the concept, strategies and concrete actions to strengthen industrial production and competitiveness in Africa.

To assist the continent to take advantage of new opportunities offered by globalization and to meet the challenge of progressive industrialization as the essence of development, UNIDO, in cooperation with African Union (AU), Economic Commission for Africa (ECA) and NEPAD, co-organized consultations and four Expert Group Meetings (EGMs) in various sub-regions. These consultations culminated in the key issues discussed by the 18th CAMI Extraordinary Conference held in Midrand, South Africa, on 24-27 September 2007.

This Extraordinary Session brought together African Ministers of Industry, African experts in industrial development and African industrialists to brainstorm on some of the key issues for Africa’s industrial development. One of the major outputs of the CAMI-18 conference was the formulation and adoption of the AU Action Plan for the Accelerated Industrial Development of Africa.

This Action Plan covers the following critical areas:

- Upgrading productive and trade capacities;

- Investment promotion, facilitation and governance enhancement;

- Creating productive, decent and sustainable work for the youth;

- Promoting energy security and powering industrial growth;

- Strengthening regional industrial innovation systems.

It also tackles a number of critical priorities at national, regional, continental, and international levels to promote the coherent industrial development of Africa. The major issues that need to be addressed include:

  - Policy on Product and export Diversification, Natural Resources Management and Development;

  - Infrastructure Development;

  - Human Capital Development and Sustainability, Innovation, Science and Technology;

  - Development of Standards and Compliance;

  - Development of Legal, Institutional and Regulatory Framework;

  - Resource Mobilization for Industrial Development

The Action Plan for acceleration of Africa’s industrialization presumes that specific measures and actions should be adopted and implemented at the national, regional, continental and international levels. National governments, in collaboration with the private sector and civil society, are expected to lead the Member States in the initiation and implementation of these activities. The Regional Economic Communities (RECs) will serve as the main agents for the promotion of industrialization at the regional level while the AU and NEPAD will, with the support of UNECA and ADB, play a similar role at the continental level.

The Action Plan recognizes UNIDO’s specific technical know-how, thorough expertise and experience in industrial programme development and implementation as a key action component for Africa’s industrialization at the international level.

The proposed Programme on Industrial Upgrading and Modernization in SADC Countries represents one of 4 sub-regional initiatives covering the Upgrading Productive and Trade Capacities area of the Action Plan. It addresses all critical priorities of the Action Plan (Priority No. ii – indirectly) and intends to develop and put in place policies and activities for upgrading manufacturing capacities, modernization of productive facilities, reinforcing the institutional support infrastructure, developing human resources, and strengthening the capacities for innovation.

  - The SADC Context

      - Economic situation

The Southern African Development Community (SADC) is composed of fifteen countries at various levels of industrial development. They are: Angola, Botswana, Democratic Republic of Congo, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, Swaziland, Tanzania, Zambia and Zimbabwe. Among these Member States, with a total of more than 200 million inhabitants, there are large differences in size, economic development, trade patterns and factor endowments. SADC comprises least developed countries, developing countries and one Newly Industrialized Country (NIC), South Africa, which accounts for over two-thirds of the region’s economy.

In spite of the economic imbalances amongst its Member States and the relatively small size of the market (only comparable to Belgium or Norway), in the African context SADC's aggregate GDP of USD 989 billion (in 2000 prices) is more than double that of ECOWAS, and equivalent to more than half the aggregate GDP of Sub Saharan Africa (SSA). It also has the highest GNI per capita in the whole of SSA. Thus, despite a relatively small market size, SADC region can still reap significant gains from regional integration, provided supply side constraints are adequately addressed.

Figure 1:

Regional Configuration of SADC Countries

The average regional GDP growth rate during the 1990s and early 2000s was significantly positive despite a slow start in 1990-1992. Economic recovery in the region started showing strong signs in 1993 and gained momentum in 1996 with a SADC average GDP growth rate of 5% (see Table 1 and Chart 3).

Table 1:

Basic Macroeconomic Indicators of SADC Region, 1997-2007

|  | 1997-2001 | 2002 | 2003 | 2004 | 2005 | 2006* | 2007* |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Real GDP Growth (%) | 2.3 | 3.7 | 3.1 | 5.1 | 5.7 | 5.5 | 7.1 |
| Real Non-Oil GDP Growth (%) | 2.4 | 3.2 | 3.4 | 4.9 | 4.6 | 6.0 | 8.1 |
| Real Per Capita GDP Growth (%) | 0.7 | 2.3 | 1.8 | 3.8 | 4.4 | 4.1 | 5.6 |
| Real Per Capita GDP (USD)** | 889 | 917 | 927 | 955 | 989 | 1,022 | 1,069 |
| Consumer Prices (Annual delta in %) | 21.4 | 17.8 | 16.7 | 10.8 | 10.6 | 14.6 | 17.3 |
| Total Investment (% of GDP) | 17.7 | 13.3 | 17.1 | 18.3 | 18.1 | 20.0 | 20.1 |
| Domestic Saving (% of GDP) | 17.6 | 14.0 | 16.8 | 18.6 | 18.7 | 20.2 | 18.8 |
| Government Revenue, Excluding Grants (% of GDP) | 23.4 | 22.3 | 23.4 | 24.5 | 26.4 | 28.2 | 28.5 |
| Reserves (months of imports of goods and services) | 3.4 | 3.6 | 3.1 | 3.4 | 3.6 | 3.9 | 3.7 |

# * 	Estimates

# ** 	At constant 2000 prices

# Source: IMF Regional Economic Outlook, 2007

Chart 3: Economic Growth Trends in SADC Region, 1997-2007

The improvement in economic performance is largely attributed to the stable and democratic political environment in the region as well as to the introduction of macroeconomic reforms in most Member States, at the end of the 1980s and beginning of the 1990s.

However, in the following years the growth pattern fluctuated considerably from year to year and reached 5.7% in 2005.  Economic performance on the whole has remained fragile and most SADC countries continue to be exposed to natural disasters and adverse external shocks. Table 2 reflects the current ranking of the SADC Member States in terms of the gross domestic product as whole and per capita as of 2006 year results.

Table 2: GDP Ranking of SADC Member States in 2006*

|  | GDP at market price, million USD | 2006 Ranking | GDP per capita, USD | 2006 Ranking |
| --- | --- | --- | --- | --- |
| Angola 1 | 47 260 | 2 | 2 882 | 6 |
| Botswana 2 | 10 050 | 5 | 5 711 | 2 |
| DRC | 8 798 | 6 | 148 | 15 |
| Lesotho | 1 443 | 14 | 806 | 9 |
| Madagascar | 5 493 | 11 | 288 | 13 |
| Malawi | 2 193 | 13 | 167 | 14 |
| Mauritius 2 | 6 424 | 9 | 5 115 | 4 |
| Mozambique | 7 262 | 7 | 360 | 11 |
| Namibia 2 | 6 248 | 10 | 3 045 | 5 |
| Seychelles 1 | 746 | 15 | 9 172 | 1 |
| South Africa 2 | 251 099 | 1 | 5 276 | 3 |
| Swaziland | 2 533 | 12 | 2 461 | 7 |
| Tanzania | 12 847 | 3 | 329 | 12 |
| Zambia | 10 945 | 4 | 923 | 8 |
| Zimbabwe | 7 034 | 8 | 538 | 10 |
| Total SADC | 379 629 |  |  |  |
| SADC Average | 27 116 |  | 2 004 |  |
| AFRICA Total, 2006 | 1 092 772 |  | 1 182 |  |

# * 	At constant 2000 prices; 1: GDP at market price; 2: GDP at basic price

Source:  African Development Bank

Driven by the need to rapidly reduce poverty, like other SSA regions, SADC has embarked on the implementation of a number of reform measures aimed at promoting macroeconomic stability and higher growth combined with the improvement in the delivery of social services.

      - Foreign Trade

Foreign trade plays an important role in the economies of SADC Member States. Trade data on SADC Member-States reveal a number of features. Firstly, trade is relatively a more important component of GDP in small countries like Lesotho and Swaziland than in large countries like South Africa.

Available data on the terms of trade show that most SADC Member States alongside with the majority of other African States have been experiencing a long-term decline in their terms of trade. This trend has been particularly persistent between 1980 and 2000. Since mid-1990s, while South Africa’s trade has surged under the post-Apartheid regime, the SADC region has remained a marginal player in the international market. With a relatively stable 0.80% share of total world exports over the decade 1992-2002, SADC has not yet been able to fully benefit from the global trade liberalization trend.

South Africa's intra-regional trade is mainly with other SACU countries due to the existence of a customs union and a common monetary area. The SADC region accounts for 19% of South Africa's total exports.  Of this, about 68% (i.e. 13% of total exports) goes to other SACU Member States. Also, South Africa's imports originating from the SADC region accounts for 7% of the country’s total imports.  Of this, 71% (i.e. 5% of total imports) comes from SACU member countries.  Lesotho depends overwhelmingly on South Africa for its export market. Of the non-SACU members of SADC, Zimbabwe and to some extent Malawi export significant proportions of their goods and services to Southern Africa, mainly in South Africa.

For the majority of the countries in Southern Africa, however, the EU is a major export market. Asian export destinations are significant for Angola, Mauritius, Mozambique, South Africa and Tanzania. The bulk of imports of SADC Member States originate in EU, USA and increasingly China (see Chart 4). For Mauritius and Tanzania, Asian sources account for significant proportions of their imports; while for Angola and South Africa, NAFTA is a significant source of their imports.

Intra-regional trade in SADC is influenced by both the SADC Trade Protocol and bilateral trade agreements, which Member States have negotiated prior to entry into force of the Trade Protocol. The Trade Protocol provides for the continuation of existing bilateral arrangements as long as they do not contradict the protocol. Intra-SADC trade is estimated at 24%, which means that the major share of trade is still with the rest of the world.

Chart 4:

Main Trade Partners, 2005

# Source: Comext (2005), EU Declaration and IMF (2004).

Total merchandise trade of the SADC increased between 1991 and 2003. SADC exports only to EU have increased by more than 173% between 1998 and 2003. The export trade for Angola, Botswana, Namibia and South Africa is dominated by oil or mineral exports. The oil and mining industry play significant roles as major foreign exchange earners and are sources of inputs for industrial development. While oil and mining ventures are capital intensive, they still generate substantial employment opportunities directly and indirectly through linkages with other supply and input sectors.

Chart 5:

SADC Main Exported Products to EU, 2005

Source: European Commission, 2005

In other countries, agricultural commodities and other unprocessed goods dominate export trade. Approximately 85% of SADC non-petrol exports are mineral and agricultural goods. The bulk of imports of SADC Member-States are intermediate and capital goods. Only South Africa and, to a limited extent, Zimbabwe have the capacity to produce such goods. This has a negative impact on the development of the region and leads to imbalances in economic levels. Furthermore, the region produces similar primary goods, which are mainly agro and mineral based.

National trade statistics show the limited diversification of exports of industrial products across the region. In most of the Member States, a few major exports constitute over half of total exports. This however varies between countries                 (see Table 3).

Table 3:

SADC Basic Exports Commodities, 2005

|  | The main 3 products exported, with their share in total exports |  |  | No of products accounting for more than 75% of exports |
| --- | --- | --- | --- | --- |
|  | Product I | Product II | Product III |  |
| Angola | Crude petroleum (95.8%) |  |  | 1 |
| Botswana | Diamonds.excl.industrial (88.2%) | Nickel mattes, sintrs.etc (8.1%) |  | 1 |
| DRC | Diamonds.excl.industrial (42.6%) | Oth.non-ferr.ore, concntr (17.2%) | Crude petroleum (16.7%) | 3 |
| Lesotho | Jersys, pullovrs, etc. knit (29.2%) | Trousers, breeches, etc. (22%) | Diamonds.excl.industrial (15%) | 4 |
| Madagascar | Jersys, pullovrs, etc. knit (19.4%) | Crustaceans, frozen (13.2%) | Spices, ex.pepper, pimento (9%) | 14 |
| Malawi | Tobacco, stemmed, stripped (59.2%) | Tea (7.6%) | Sugars, beet or cane, raw (5.3%) | 4 |
| Mauritius | Sugars, beet or cane, raw (21.4%) | T-shirts, othr.vests knit (18.7%) | Shirts (7.6%) | 10 |
| Mozambique | Alum., alum. alloy, unwrght (73.4%) | Crustaceans, frozen (4.7%) |  | 2 |
| Namibia | Diamonds.excl.industrial (39.1%) | Radio-active chemicals (11.4%) | Zinc, zinc alloy, unwrght. (9.7%) | 5 |
| Seychelles | Fish, prepard, presrvd, nes (44.1%) | Fish, frozen ex.fillets (27.5%) | Ships, boats, othr.vessels (11%) | 3 |
| South Africa | Platinum (12.5%) | Oth.coal, not agglomeratd (8%) | Gold,nonmontry excl ores (7.9%) | 39 |
| Swaziland | Sugars, beet or cane, raw (14.1%) | Food preparations, nes (9.3%) | Flavours,industrial use (9%) | 20 |
| Tanzania | Gold, nonmontry excl ores (10.9%) | Fish fillets, frsh, chilld (9.7%) | Copper ores, concentrates (8.6%) | 15 |
| Zambia | Copper; anodes; alloys (55.8%) | Cobalt, cadmium, etc.unwrt (7%) | Cotton, not carded, combed (5.7%) | 5 |
| Zimbabwe | Tobacco, stemmed, stripped (13.9%) | Nickel, nckl.alloy, unwrgt (12.6%) | Nickel ores, concentrates (12.3%) | 16 |
| Africa* | Crude petroleum (49.2%) [18%] | Diamonds.excl.industrial (3.7%) [12.6%] | Nickel ores, concentrates (2.8%) [17.5%] | 26 |

* Figures in [  ] represent the share of Africa in the World export for each product.

Source : PC-TAS 2001-2005 International Trade Center UNCTAD/WTO.

The following table provides the exports diversification indicator measuring the extent to which exports are diversified. It is constructed using disaggregated exports at 4 digits (following the Standard International Trade Classification Revision 3 (SITC3)). A higher index indicates more export diversification.

Table 4:

#### Exports Diversification Index in SADC Member States, 2000-2005

|  | Exports Diversification index |  |  |  |  | Annual export growth, 2001-2005 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2001 | 2002 | 2003 | 2004 | 2005 |  |
| Angola | 1.3 | 1.2 | 1.1 | 1.0 | 1.1 | 51.0% |
| Botswana | 7.5 | 1.3 | 1.3 | 1.4 | 1.3 | 369.7% |
| DRC | 2.4 | 1.8 | 2.8 | 3.8 | 4.1 | 3.5% |
| Lesotho | 5.2 | 5.1 | 5.4 | 5.1 | 5.6 | 25.5% |
| Madagascar | 9.2 | 8.4 | 7.6 | 10.7 | 12.2 | 0.1% |
| Malawi | 2.9 | 2.9 | 3.3 | 3.7 | 2.8 | 5.7% |
| Mauritius | 12.6 | 12.2 | 11.8 | 10.3 | 9.9 | 1.4% |
| Mozambique | 2.9 | 2.7 | 2.3 | 1.9 | 1.8 | 28.9% |
| Namibia | 7.1 | 7.2 | 10.3 | 7.0 | 5.2 | 56.5% |
| Seychelles | 2.6 | 2.8 | 2.4 | 3.1 | 3.5 | 17.4% |
| South Africa | 33.2 | 31.2 | 27.7 | 25.3 | 23.1 | 11.2% |
| Swaziland | 8.8 | 13.9 | 15.7 | 15.0 | 18.9 | 28.4% |
| Tanzania | 19.0 | 21.0 | 24.1 | 22.0 | 18.7 | 21.1% |
| Zambia | 4.2 | 4.3 | 5.0 | 3.6 | 3.1 | 32.7% |
| Zimbabwe | 9.8 | 7.8 | 10.7 | 12.2 | 13.9 | 0.1% |
| Africa | 8.1 | 8.0 | 6.3 | 5.1 | 4.1 | 21.4% |

Source: PC-TAS 2001-2005 International Trade Center UNCTAD/WTO.

The reason for such a poor exports pattern mainly consists in the fact that SADC exporters have no or small experience of international markets standards, and an insufficient knowledge of the demand to adapt their production accordingly. The non-tariff obstacles (standards for instance), the insufficient quality, quantity and competitiveness limit the possibilities to access foreign markets like EU.

As many other developing countries, the SADC countries will have to improve their commercial policy and strategy, legal environment for international trade and investments, institutional support to industry, public-private partnership in order to realise the desired impact on their international trade.

  - Industrial sector analysis

      - General overview

The industrial base of Southern Africa is weak and its contribution to the GDP is minimal. Most countries in the region are characterized by the predominance of small industrial units, which mostly produce for the national and regional markets. The industrial sector of the region is nearly excluded from international competition, especially where protectionist policies are practiced.

The structure of SADC countries output is typical for a developing region where large shares of GDP originate from primary sectors. Thus, agriculture plays a key role in forming the national product in Tanzania, Malawi and Madagascar and mining sector leads economies in Botswana and South Africa, where total contribution to GDP is greater than the half of cumulated value-added. At the same time, most of the crops, livestock and fish, for instance, are marginally exported and just few mining products are not locally processed.

Table 5:

Structure of GDP in SADC, 2006

|  | Agriculture |  |  | Industry |  |  | of which manufacturing |  |  | Services |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Average 2000-2005 | 2006 | 2006 ranking | Average 2000-2005 | 2006 | 2006 ranking | Average 2000-2005 | 2006 | 2006 ranking | Average 2000-2005 | 2006 | 2006 ranking |
| Angola | 7,6 | 6,7 | 11 | 63,3 | 59,5 | 1 | 3,6 | 3,4 | 15 | 29,2 | 33,8 | 14 |
| Botswana | 2,4 | 2,4 | 15 | 55,4 | 52,8 | 2 | 4,3 | 3,9 | 14 | 42,2 | 44,9 | 10 |
| DRC | 51,1 | 44,9 | 1 | 21,8 | 25,3 | 11 | 5,2 | 5,7 | 13 | 27,1 | 29,8 | 15 |
| Lesotho | 17,0 | 16,4 | 8 | 41,7 | 42,4 | 4 | 18,4 | 15,4 | 4 | 41,3 | 41,3 | 11 |
| Madagascar | 29,2 | 27,5 | 4 | 15,1 | 15,7 | 14 | 11,9 | 12,5 | 8 | 55,8 | 56,7 | 6 |
| Malawi | 38,4 | 35,6 | 3 | 17,2 | 18,6 | 12 | 11,7 | 11,7 | 10 | 44,4 | 45,8 | 9 |
| Mauritius | 6,5 | 5,3 | 12 | 29,9 | 27,3 | 9 | 21,9 | 19,6 | 2 | 63,6 | 67,4 | 2 |
| Mozambique | 22,3 | 19,9 | 6 | 25,7 | 25,8 | 10 | 13,0 | 12,9 | 6 | 52,0 | 54,3 | 7 |
| Namibia | 11,1 | 12,1 | 9 | 29,6 | 28,4 | 8 | 11,5 | 11,6 | 11 | 59,3 | 59,5 | 5 |
| Seychelles | 2,8 | 2,7 | 14 | 29,0 | 28,8 | 7 | 17,2 | 15,2 | 5 | 68,1 | 68,5 | 1 |
| South Africa | 3,4 | 2,7 | 13 | 31,7 | 30,6 | 6 | 19,1 | 18,3 | 3 | 64,9 | 66,7 | 3 |
| Swaziland | 12,9 | 10,1 | 10 | 46,8 | 50,5 | 3 | 37,3 | 36,6 | 1 | 40,3 | 39,4 | 12 |
| Tanzania | 45,3 | 45,9 | 2 | 16,3 | 17,0 | 13 | 7,2 | 7,0 | 12 | 38,4 | 37,0 | 13 |
| Zambia | 22,6 | 21,3 | 5 | 27,0 | 31,2 | 5 | 11,7 | 11,9 | 9 | 50,4 | 47,5 | 8 |
| Zimbabwe | 20,0 | 18,1 | 7 | 14,5 | 15,4 | 15 | 11,1 | 12,7 | 7 | 65,4 | 66,5 | 4 |
| SADC Average | 19,5 | 18,1 |  | 31,0 | 31,3 |  | 13,7 | 13,2 |  | 49,5 | 50,6 |  |
| AFRICA |  | 13,8 |  |  | 41,5 |  |  | 10,9 |  |  | 44,7 |  |

Source:  African Development Bank, 2007.

The above figures show that only Swaziland and Mauritius possess considerable manufacturing sectors producing around 20-35% of GDP.  The Swaziland’s industrial performance is mostly due to the emerging textiles sector, which benefited from the favourable export framework within AGOA agreement with USA. The once significant manufacturing sector of Zimbabwe has stalled under the several factors, including the flow of cheap foreign merchandise, higher input costs and shortages in foreign exchange for imported raw materials and components. Its national economy has gradually become more reliant on services.  The rest of SADC countries have relatively small manufacturing sectors relying mostly on services, agriculture or mining.

Angola has developed its industry essentially based on raw petroleum and non-manufacturing production, and Botswana bases on services, which represented 45% of its GDP (2006). Other SADC economies are just below the African average, and Tanzania up to now has never been a large manufacturing country.

Referring to the contribution of manufacturing sector to the annual GDP growth in 2006, Swaziland registered an increase of 36%, followed by Mauritius (19,6%) and South Africa (19,3%). However these figures are not representative of the entire region as Swaziland’s economy is relatively small whilst Mauritius and South Africa have longer “industrial” traditions and permanent support in developing national productive capacities and as result, their regional leadership in industrial and overall economic performance.

The chart below shows that in SADC countries, the industrial sector’s contribution to the GDP varies from 15.4% in Zimbabwe to 59.5% in Angola (2006). On average, the industrial sector of SADC countries represents 31.5% of the GDP.

Chart 6:

Share of Industry and Manufacturing Sector to National GDP, 2006

Source:  African Development Bank, 2007.

The share of manufacturing sector in GDP is also quite dissimilar and rarely correlates with industrial sector’s contribution due to the part played by extraction industries in economies of some SADC countries. In particular, it ranges along 3.4% in Angola with its strong oil production sector to 36.6% in Swaziland with the SADC average of only 13,1%, which is above the African average of 10,9%.

With its vast amount of natural resources, trained manpower and a market of several millions of people, the Southern Africa region possesses a great potential to succeed in all segments of industrial value chain.

Along with national industrialization strategies, the regional distribution of the value chain cannot be neglected, as it could provide additional value-added to the region if such issues as harmonization of industrial and trade policies as well as competitive trade and manufacturing of goods are addressed.

      - Manufacturing Sector

The “formal” manufacturing sector in SADC is largely dominated by the textile sector, followed by the agro-food processing industries. Mineral processing, chemical and pharmaceuticals, contribute relatively little to the regional value-added, each bringing only about 1-2% on average to SADC manufacturing value-added.

Most of the geographical clustering within the formal sector is centered around primary industries, i.e. mining, agriculture and the primary agro-food processing industry. With the exception of the mining industry, the private sector in Southern African region has not been instrumental in creating and sustaining successful and competitive manufacturing networks within formal environment due to the relatively high taxes and other numerous cost-increasing factors. Thus, SADC’s formal manufacturing sector has not developed much against the background of emerging informal sector.

Table 6:

Manufacturing Companies in certain SADC countries, 2007

|  | Angola | Botswana | DRC | Lesotho | Madagascar | Malawi | Mauritius | Mozambique | Namibia | Swaziland | Tanzania | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Textiles, weaving apparel, carpets/rugs | - | 1350 | 3 | 30 | 557 | 92 | 371 | 898 | 18 | 20 | 49 | 3388 |
| Food, beverages and tobacco | 50 | 363 | 24 |  | 239 | 470 | 127 |  | 116 | 30 | 148 | 1567 |
| Sawmill, wood and furniture | 6 |  | 42 |  | 208 | 138 | 46 |  | 23 |  | 28 | 491 |
| Processing of minerals metallic & non-metallic | 8 |  | 10 |  | 120 | 23 | 95 | 410 | 28 |  | 71 | 765 |
| Domestic plastic and rubber products | 16 |  | 11 |  | 90 |  |  |  |  |  |  | 117 |
| Chemicals and pharmaceuticals | 20 |  |  |  | 24 |  | 68 | 3 | 24 |  | 28 | 167 |
| Pulp, paper, printing and publication | 10 |  | 8 |  | 40 |  | 33 |  | 20 |  | 47 | 158 |
| Fabricated metal products | 12 |  | 12 |  | 14 | 38 | 79 |  |  |  |  | 155 |
| Other manufacturing | 8 | 982 |  | 14 | 12 | 50 | 89 |  | 49 | 191 |  | 1395 |
| Total | 130 | 2695 | 110 | 44 | 1304 | 811 | 908 | 1311 | 278 | 241 | 371 | 8203 |

Source: Data collected from different sources by UNIDO Programme Formulation Mission

Angola once had one of Africa’s most developed manufacturing industries, but the civil war led to a prolonged phase of negative growth. There are signs, however, that production is picking up in certain industries, as consumers’ purchasing power recovers in Luanda and other major urban centres. The sector recorded a cumulative growth rate of 67.4% in real terms for the 2000-04 period, 24.9% in 2005 and 30.7% in 2006. The beverages sector, for instance, grew by 8% in 2005 and is estimated to have grown even more in 2006. In general, agribusiness is expected to benefit from the recent opening of cold-storage facilities in Luanda and the announcement of a rehabilitation programme for the national cold-storage network.

The industrial sector of Botswana is dominated by textiles production with 1350 enterprises representing almost half of the country’s manufacturing companies and employing a third of the local working-age population (2005), followed by the food and beverages manufacturing companies with 363 enterprises operating and 18% of the total labor employed in the sector.

Industrial sector of Democratic Republic of Congo supplied 13.7% of GDP in 2005 and grew 9.3% in volume, with construction and beverages taking the lead. Alcoholic beverages, especially beer, showed a 18.9% growth rate in 2005; cement production grew in volume by 26.2% mainly due to the country’s reconstruction and huge needs. Log production increased substantially, by 16.8% in 2005 and by 54% in the first five months of 2006. The DRC possesses enormous mineral and agricultural potential, serving as the basis for industrial diversification and deeper local transformation. Traditionally, numerous entrepreneurs in DRC operate small- (3-4 employees) and medium-sized businesses in the informal sector.

Manufacturing sector of Lesotho is mostly active in and relying on textiles and garment branch (60% of enterprises and 95% of employment) as country continues to enjoy the benefits of AGOA agreement. However, there is a fear that Lesotho and Madagascar could become too dependent on this particular productive activity and therefore vulnerable to trade liberalization.

The manufacturing landscape in Madagascar can be divided into various industrial groups and sub-groups, where textile sector is, as mentioned above, one of the socio-economic pillars giving employment for 62% of the working-age population and accounting 557 producers (43% all formal sector local companies). In general, the industrial sector of Madagascar is significantly more diversified relative to the common SADC pattern. Mining sector is represented by a significant number of manufacturing enterprises operating mainly in gemstones processing. In general these companies employ less than 10 persons.

Malawi’s manufacturing sector is small and accounts for just about 11% of GDP.  The sector is dominated by agro-processing industries.  These include tea factories, spinning and weaving, tobacco processing, sawmills and plywood, oil and grain mills, meat processing. Other industries include soaps and detergents, cement, textiles and clothing, footwear, leather processing, fertilizer compounding, brewing, distillery and structural works. The manufacturing sector is also inward-looking as shown by the fact that only 14% of manufacturing output is exported.

The traditional productive sectors in Mauritius, sugar and textile, have accounted for 12-14% of GDP, 20-25% of employment and 40-50% of foreign exchange earnings.  With its highly qualified human capital, good road network, modern telecommunications facilities, modern airport, deep-water harbour, island-wide electricity and adequate water supply, Mauritius has what it takes to develop its industrial sector.

Mozambique has an agriculturally based economy thus its manufacturing industry is centred mostly in food processing and beverages (food, beverages, and tobacco processing account for 62% of all manufacturing). Mozambique's manufacturing sector is primarily engaged in the processing of locally produced raw materials, such as sugar, cashews, tea, and wheat. Brewing and textile production emerged in the 1980s, along with cement, fertilizer, and agricultural implement manufacturing. Other industries produce soaps, oils, ceramics, paper, railway equipment, radios, bicycles, and matches. Production of aluminum by Mozal makes Mozambique one of the world’s leading aluminum exporters.

Namibia has a relatively small manufacturing sector, which is largely based on its natural resource endowment and mainly concentrated on processing fish, fisheries products, livestock and livestock products and minerals.  Other manufacturing activities include food, beverages, textiles, wood and wood products. In 2005-2006 manufacturing accounted only 11% of GDP and recorded growth of -0.6%, owing to the poor performance of fish processing.

Seychelles has a small manufacturing and processing sector, oriented towards supplying the domestic market. Most of the industries are of small and medium scale. The sector consists a brewery SeyBrew which is part of the Guinness group, a cigarette factory Amalgamated Tobacco, the Seychelles Marketing Board responsible mainly for Agro-food processing such as jam, juices, yogurt, water, crisps and snacks, etc. and a number of small enterprises making soap and detergents, processing corrugated iron sheets, assembling televisions, fabricating boats and furniture, mixing paints, and distilling local liqueurs. At the fringe of the "industrial sector" is the handicraft sector dominated by the SMEs. Some of its products are effectively exported (sold to tourists) and are included into the tourist sector accounts.

South Africa has developed an established, diversified manufacturing base that has its resilience and potential to compete in the global economy. The sector is dominated by agro-processing, automotive, chemicals, ICT and electronics, metals, textiles, clothing and footwear and heavily concentrated in the urban areas especially in the industrial region around Johannesburg, Cape Town, Port Elizabeth and East London. As the manufacturing sector expanded, the sector became increasingly capital intensive despite the availability of the large labor pool in South Africa. Country’s manufacturing sector provides a locus for stimulating growth of other activities, such as services, and achieving specific outcomes, such as employment creation and economic empowerment. This platform of manufacturing presents an opportunity to significantly accelerate the country’s growth and development.

During the last decade, Swaziland’s productive sector has been characterized by a slow-down in growth and stagnation in FDI flow into the sector. The country’s top three exports in total value over the last five years are edible concentrates, sugar and wood pulp. The mining sector, which is focused on coal and diamonds for export, contributes a mere 1.8% to GDP and has been declining in importance in recent years. The sectors that take up a major part of the industrial pool are food processing (i.e. food, beverages and dairy), engineering and construction, textile and clothing.

Industrialization in Tanzania is relatively lower, with a heavy emphasis on traditional agriculture. Tanzania’s manufacturing is one of the least developed and stagnating in Sub-Saharan Africa producing only US $15.5 as manufacturing value added (MVA) per capita. Tanzania relies on its agriculture, trade, and strong tourism sector (restaurant and hotels).

The leading manufacturing sub-sectors of Zambia are food, beverages, and tobacco, accounting for over two-thirds of total value added, followed by textiles, leather, and leather products where Zambia has comparative advantage. The performance of the food, beverages, and tobacco sub-sector is driven by the strong agricultural sector, increases in domestic demand and exports to regional markets. Textiles and leather were stimulated by the increased production of cotton lint and yarn, direct exports to the USA under the AGOA arrangements and increased investments in cotton processing. The other significant sub-sectors are chemical rubber and plastics and wood and wood products.

Since the beginning of 1999, the Zimbabwean productive sectors became embroiled in a series of economic challenges continuously affected by a drastic upsurge in the inflationary pressure. The real state of manufacturing sector has declined over the years in response to trade liberalization in general and to negative trading environment caused by foreign currency shortages, power cuts, loss of credit lines, and escalating costs of raw materials over the past four years. Nonetheless, Zimbabwe’s manufacturing production structure remains diversified from consumer goods to a wide range of intermediate and capital goods. The largest industries are iron, steel, metal products, food processing, chemicals, textiles, clothing, furniture and plastic goods. The three most promising cluster-based sub-sectors are engineering and metal working industries, agro-industries/food, and textile and garments.

      - Priority Sectors

The study undertaken by UNIDO in 2003 under African Productive Capacity Initiative (APCI) has identified nine priority sectors to kick-start the regional industrialization process. Following several meetings at both Regional and Sub-regional levels, the SADC Ministers of Industry and Trade adopted the following sub-sectors as strategic: Agro-food processing; processing of Minerals (metallic and non-metallic) products; Leather and leather products; Forestry; Fisheries; Chemicals, Petroleum and Pharmaceuticals; Textiles and garments; Machinery and Equipment; and Services.

The SADC Ministers of Industry and Trade decided that strategies and action plans should be developed, with the assistance of UNIDO, at both the SADC Regional level and national levels to improve industrialisation and promote employment in the SADC region.

Of the nine priority sectors, the pilot phase of the Programme will focus – subject to degree of importance for the certain countries – on the following three: agro-food processing, minerals processing, and pharmaceuticals.

Agro-food processing has the potential for ensuring food security, employment creation, especially at the rural level, improving household income, contributing to economic diversification.  Minerals processing will increase the foreign exchange earning potential of SADC Member States, facilitate infrastructure development, as well as provision of social facilities, and attract FDI.  Developing the pharmaceuticals sector will provide medicines for ailments such as HIV/AIDS, tuberculosis, and malaria, exploit potentials for developing the local cosmetics industry, employment creation especially for rural women, sustainable harvesting of natural medicinal plants and herbs, environmental protection and promotion of medical tourism.

In addition, sectors possess a great growth and export potential. The specific feature of agro-food and mineral processing sectors consists in relative advantage of gaining in competitiveness at fewer costs through adapting the final production to international quality and security standards.

The following is a brief summary of the current situation overview followed by SWOT analysis for each of three priority resource-based sectors:

- Agro-food processing

Like most developing countries, agriculture is the cornerstone of the SADC countries economies. Unfortunately, agriculture alone is no longer able to provide reliable livelihood for the growing population in SADC.  In spite of its tremendous potential, agricultural goods account for only 8% of the region’s overall exports trade with the EU.

Success in the agri-business at the global export level lies in a world-class research system, priority attention to phytosanitary and sanitary issues, and well-established networks in key markets. Therefore, to achieve success in the agro-food processing sector in Southern Africa, the two non-negotiable pre-requisites – before one can even begin to contemplate exporting food (fresh or processed) – are Quality and Phytosanitary and Sanitary Assurance.

Development activities should concentrate on creation of the regulatory environment favorable to the agro-food industry, including the up-keep of exports of non-processed food products for a period of at least 5 years; adoption of more flexible labor regulation, which come across with seasonality of the sector; establishment of processing incentives and institutional capacity building for coordination and leadership of the technical, technological, and industrial framework. In particular, a lot of effort is needed in the following areas: Inspection, control and testing of products; Reduction of post-harvest losses; integral management of food crops; micro finance (credit)/rural finance (credit); export marketing research; and environmental protection.

The following strengths, weaknesses, opportunities and threats associated with the agro-food processing industry in SADC were identified.

SWOT and Challenges of SADC Agro-food Sector

| # Strengths ## Existence of raw materials/conditions for production of raw materials ## Production of some world-class products ## Support at all Governmental levels ## - Programmes ## - Financial support ## Existing processing plants/capacity ## Fairly large market in SADC; Africa | # Weaknesses ## Unintegrated industrial development structures ## Limited value addition ## Inadequate marketing and export market access ## Lack of farming infrastructure ## Lack of technical & management skills ## Lack of external trade strategy (strategic protection, promotion, market intelligence, etc) ## Low R&D (infrastructure and spend) ## Poor/inadequate, disintegrated transport infrastructure (ports, rail, air-cargo, road) |
| --- | --- |
| # Opportunities ## Growing demand for finished products worldwide ## Growing SADC & African market ## Labour-intensive production processes ## Growth opportunities in China and India market | # Threats ## Low quality & quantity of raw materials ## Unstable supplies of raw materials ## Recurrent drought and seasonality of supplies ## High transportation costs ## Lack of credit facilities ## Existence of TBTs, NTBs/SPS ## Interventionist policies of export countries ## HIV/AIDS |

# Challenges ## Poor product quality ## Limited market access due to barriers to trade (TBTs; NTBs/SPS) ## Limited marketing due to problems with pricing, limited margins and inadequate promotions strategies ## Inadequate/weak Human Capital development ## High transaction costs ## High transportation and logistics costs ## Weaknesses in provision of relevant information ## Poor/lack of coordination in infrastructure development ## Restrictive regulatory environment ## High cost of doing business ## HIV / Aids

- Minerals processing

The Southern African region produces significant quantities of major metals and minerals. It contributes about 53% of vanadium, 49% of platinum, 40% of chromite, 36% of gold, 50.1% of diamonds and 20% of cobalt to the world production. A number of countries in Southern Africa rely on this sector for their foreign exchange earnings and there is potential for investment and wealth creation opportunities.

Table 7:

SADC Mineral Production, 2003

|  | Units | SADC | Africa | % Africa |
| --- | --- | --- | --- | --- |
| Aluminium | tonnes | 1 146 500 | 1 440 000 | 79.6 |
| Bauxite | tonnes | 11 793 | 15 500 | 76.1 |
| Chrome | tonnes | 8 071 748 | 8 130 000 | 99.3 |
| Coal | tonnes | 242 572 778 | 244 000 000 | 99.4 |
| Cobalt | tonnes | 15 775 | 25 000 | 63.1 |
| Copper | tonnes | 535 131 | 551 000 | 97.1 |
| Diamond | cg | 80 084 603 | 82 755 603 | 96.8 |
| Gold | kg | 436 237 | 587 000 | 74.3 |
| Iron Ore | tonnes | 38 485 855 | 53 100 000 | 72.5 |
| Nickel | tonnes | 77 742 | 85 300 | 91.1 |
| Palladium | kg | 74 116 | 74 116 | 100 |
| Platinum | kg | 152 746 | 152 748 | 100 |
| Uranium | tonnes | 3 419 | 5 940 | 57.6 |

Source: Mintek, South Africa, 2006

Mineral processing continues to be a major sector of the economies of the region, contributing an average of about 60% of foreign exchange earnings, 10% of gross domestic product and 5% of employment in the region.

The strengths, weaknesses, opportunities and threats associated with the mining and minerals processing industry in SADC were identified. These include:

SWOT and Challenges of SADC Mineral Processing Sector

| # Strengths ## Rich endowment with various minerals deposits ## Conditions for its production ## Strong capabilities in upstream industries ## Support at all Governmental levels ## Primary production being done ## Limited production at downstream levels ## Existing processing plants/capacity | # Weaknesses ## Unintegrated industrial development structures (i.e. weak linkages) ## Limited value addition in downstream industries ## Poor quality of products ## General lack of QC & QA no common quality standards ## Slow speed of delivery due to poor/inadequate, unitegrated transport infrastructure (ports, rail, road) ## Low investment in minerals processing ## Shortage of skills – artisan, technical, engineering, managerial levels => low production capabilities in downstream industries ## Lack of technology support structures ## Low R&D (infrastructure and spend) ## Inadequate marketing and export market access ## Lack of external trade strategy (strategic protection, promotion, market intelligence, etc) ## Lack of credit facilities |
| --- | --- |
| # Opportunities ## Growing global demand for finished mineral products ## Growing global trade in scrap & recycling ## Growing African market ## Labour-intensive production processes ## Under-developed downstream industries (electronics, industrial machinery and equipment, transportation, construction, automotives, etc) ## Growth opportunities in Asian market (esp. China and India) | # Threats ## Import-parity pricing of basic metals by upstream minerals processing companies who are very few, but have significant price-setting power ## Interventionist policies (e.g. subsidies) in scrap importing countries ## Increasing emphasis on environmental, health and safety standards => higher costs ## Differential pricing of inputs (e.g. electricity: pre-negotiated prices for upstream companies; municipal rates for downstream companies) ## High transportation costs ## Aging workforce ## Existence of TBTs, NTBs ## HIV/AIDS |
| # Challenges ## Skills development and training ## Improving logistics to reduce the cost of manufacturing ## Facilitating import replacement ## Enhancing production capabilities ## Encouraging advanced manufacturing and technologies ## Building a competitive foundry industry ## Provide information/data on imports to industry (Early Warning System) |  |

- Pharmaceuticals

The global pharmaceutical industry (i.e. discovery, development and distribution) is characterised by its large size, high growth, globalisation and high investment in R&D. It is a multinational industry that is highly regulated, capital intensive and driven by large R&D expenditures. The global market (pharmaceutical and bio-technology) is estimated to be currently valued at about $552 billion in 2006 and growing at approximately 8 percent. The U.S. market accounted for about 41 percent of the global pharmaceutical sales, followed by Europe (23.5%) and Japan (15.9%).

Globally, the pharmaceuticals industry operates as a cartel, with only a few manufacturers (i.e. Merck, Bristol-Myers Squibb, GlaxoSmithKline plc, Pfizer Inc., Johnson and Johnson, AstraZeneca, Bayer, Novartis, Aventis, etc) dominating and literally dictating the pace and level of development. Naturally, entry into the industry is very restricted and requires political will and great determination if one is to break into the elite club of industry leaders. Much of the growth during the next 5 to 10 years will come from the Asia-Pacific and Latin America regions. The Indian pharmaceutical industry currently estimated to be worth about $6 billion, and growing at about 12% annually, is expected to reach $9.48 billion in the next four years.

The pharmaceuticals industry in SADC is somewhat fragmented and there is only limited local production of generic active ingredients. However, formulation and last step synthesis is common among the local subsidiaries of multinationals.

The scope for development of pharmaceutical products is very large in SADC and the rest of Africa. Products such as gelatine capsules, bulk drugs, medicaments, disposable syringes, perfusers and diffusers are in high demand in the domestic as well as export markets. However, the sector’s part in the SADC cumulative exports to the EU, the region’s main trade partner, is miserable and estimated below 0.5%.

The potential exists in SADC and Africa for developing a vibrant pharmaceuticals/medical/biotechnology industry. More importantly, the importance of the concept of value chain within the Pharmaceutical sector is recognized.

The strengths, weaknesses, opportunities and threats of a SADC/African pharmaceuticals sector were identified as follows:

SWOT and Challenges of SADC Pharmaceutical Sector

| # Strengths ## Abundant raw materials available in the region ## Existing processing plants/capacity ## Existence of a large pharmaceutical-manufacturing sector in the region ## Existence of Standards Bureaus to foster acceptance and implementation of Quality Systems ## High quality of technical and science skills in South Africa, Zimbabwe and Mauritius universities | # Weaknesses ## Shortage of experience amongst technical staff in commercializing research ## Un-integrated industrial development structures ## Varied regulatory and procedural requirements of each member state ## Fragmentation of various industrial components ## Lack of access to capital ## Lack of technical & management skills ## Low R&D (infrastructure and spend) |
| --- | --- |
| # Opportunities ## Prevalence of curable diseases in Africa and LDCs ## Pharmaceuticals products worth billions of US$ imported by SADC member states annually ## Sector has tremendous potential for making signify-cant contributions to SADC economy, but much has to be done to make sector viable and sustainable ## Region imports pharmaceutical grade sugar and starch readily available in the region ## Int’l segmentation of the production process ## Potential for developing biotech industry | # Threats ## Aggressiveness of international drug manufacturing companies towards new entrants ## Existence of strict regulations in export markets ## HIV/AIDS |

# Challenges ## Attracting and retaining skilled workforce ## Controlling operating and marketing costs ## Competition from Generics ## Intellectual Property protection ## Managing regulatory compliance ## Pricing pressures and shrinking margins ## Marketing (Pricing; Margins; Promotions) ## Realising tangible value from strategic alliances, joint ventures and partnering arrangements ## Reputation management ## Successfully developing innovative drugs and enhancing Research & Development productivity ## Sustaining growth in global markets ## Information ## Infrastructure ## HIV/Aids

- Textiles and Garments

In addition to the priority sectors determined by the Regional Road Map, some SADC Member States could express significant interest in improving capacities of textile and garment production facilities. In the last several years, some of the region’s economies (Lesotho, Madagascar and Swaziland) have recorded considerable growth in textile sector outputs largely due to preferential trade in the framework of AGOA White Paper. The textile sectors of Botswana, Lesotho and Madagascar account respectively 51%, 68% and 43% of all manufacturing companies currently operating in these countries. The Programme considers upgrading and modernization activities for the SADC textile companies indispensable looking forward the possible liberalization of trade and intensified pressure from the Asian competitors.  Below is a short summary of the current situation in SADC textiles and garments sector.

Chart 7:

Increasing Share of Textiles in Exports, 2006

Source: IMF, 2007

The textile production in SADC region is mostly concentrated in Botswana, Lesotho, Mauritius, Madagascar, Swaziland and South Africa. Although SADC produces cotton, textiles and clothing they are not necessarily linked in the value chain.  Exports focused on preferential markets, hence are mainly basic items that have long production runs, low labor content and few styling changes.

The textiles and clothing originated from SADC countries are mainly exported to OECD countries. The United States and European Union are the largest buyers of Southern African (see table below).

Table 8:

Region’s largest exporters of textiles and garment

| SADC largest exporters to the USA | SADC largest exporters to the EU |
| --- | --- |
| Lesotho | Mauritius |
| Mauritius | Madagascar |
| South Africa | South Africa |

Source: Imani Development

In spite of relative gains of certain producers in international markets the textile sector of the region faces some typical for Sub-Saharan Africa and for other sectors principal challenges. Notably, they are:

- Lack of investment and often obsolete technologies,

- Low professional skills base and lack in on-job training facilities,

- Nearly inexistent innovation and design capacities,

- Production and design of higher value added products currently being shed by advanced economies,

- Internal firm-level competitiveness and inability to compete internationally,

- Weak or extremely spread value chains,

- Trade distortions, growing illegal imports and preference erosion,

- Complex and restrictive Rules of Origin in the main importing countries.

Meanwhile the region posses a number of inherent competitive advantages based on:

- Low wages and taxes in some countries,

- Stable secondary supply base for large global retailers who seek to diversify their sourcing and spread their risk,

- Proximity to the raw material sources,

- Proximity to Europe and the east coast of the US,

- Language and time zone advantages,

- Ethical production.

To compete within the new open-market environment most of the SADC manufacturers will need to reengineer and upgrade their operations through development of an integrated value chain and advanced supply chain management.

      - Informal sector

Based on the interviews undertaken during the formulation mission, it has been noted that no exhaustive study of the informal sector for the SADC region has ever been made. However, the results of surveys conducted in Namibia (in 2004) and Mozambique (in 2005) can provide guidelines for general conclusions for most countries in the region.

The industrial base of the SADC region is characterized by a significant number of small and medium enterprises (SMEs) operating in the informal sector.  Despite the absence of accurate statistics, it has been observed that the informal sector is relatively dynamic in basic transformation activities and services. Indeed, the myriad of “informal” small craftwork shops, workshops and small industries cannot be ignored.  The size of the informal sector determines its impact on the economies in most of the SADC countries. The informal sector does not only deprive the Member States of important fiscal revenues but also weaken their efforts to formulate and carry out sound structured economic and development policies.

One of the major reasons for not registering with the authorities is the fear that registration might lead to disadvantages. The registration process is seen as a burden and represents an operating disadvantage. “Informal enterprises” do not have to operate under the same standards (safety, quality) and regulations and have an unfair advantage over the formal enterprises that do comply with the system’s regulations and fiscal rules.

Whether in the rural or urban areas, most enterprises operating in the informal sector usually employ unskilled and uneducated workers. Also, some educated young graduates have (or will have) to enter the informal sector as the opportunities in the formal sector are limited and do not enable all graduates to find a job. This educated youth often see the informal sector as an opportunity to become entrepreneurs.

The Industrial Upgrading and Modernization Programme does not aim to solve all the problems of and linked with the informal sector. However, the Programme sees the informal sector as a pool of potential entrepreneurs, which can become effective businessmen. With some assistance, they could integrate into local value chains, become key actors in the fight to alleviate local poverty, contribute into the local development, especially in rural areas, ensure the modernization of the most remote areas through technology transfers and the introduction of basic standards and new techniques, and improve social security by creating sustainable activities.

The basic features of informal sector companies in SADC could be in general summarized as follows:

- the majority of businesses are small with high competition among each other;

- a large number of operators started a business due to a lack of alternatives or other reasons, but not because of a personal motivation;

- the fact of having informal competitors represents a competitiveness disadvantage for formal businesses;

- most businesses are less than 5 years old and there are no moderate start-up and closure rates;

- the employment dynamics for the SMEs are moderate: contrary to popular belief, they do not seem to be a powerful job engine;

- the usage of existing financial services among SMEs is fairly modest but this is mainly due to fundamental structure and character of SMEs operators;

- only very few businesses have business linkages;

- in addition, these linkages are of a very simple nature and have limited profits;

- the majority of businesses do not make use of BDS, but a large proportion uses market-related business services.

  - Strengths and challenges of manufacturing sector

      - Advantages and opportunities

The SADC region possesses a great economic and industrial potential with abundant natural resource base. Its comparative advantages include also the low-cost and qualified labour force and high opportunities for economies of scale within the growing and liberalizing regional market. The key challenge for the region is to boost economic growth through effective integration of available resources and building intra-regional industrial value chains under the leadership of region’s top economy South Africa.

SADC minerals and agro-food processing sub-sectors in particular have significant local and global comparative advantages, which can easily transform into real net winning advantages if value chains approaches are introduced and implemented gradually as a new systemic approach to sustainable industrial performance in Southern Africa.

Moreover, there is a clear perception and strong commitment by the regional authorities to industrialize. Current policies and strategies being pursued in the region under the auspices of SADC focus on export promotion, promotion of industrial linkages, efficient import substitution, improvement of the investment climate, facilitation of imports of essential goods, regional human development, enhancing industrial support services, equitable distribution of industrial activity and adopting flexible market oriented exchange rates. The Regional Indicative Strategic Development Plan (RISDP) is, in a sense, a strategic framework pointing the general direction in which SADC would like to move with respect to the identified priority industrial issues.

The energy sector, telecommunications and water supply are also largely supported by the political environment, and therefore enjoy relative advantage compared to the average picture for Sub-Saharan Africa. The transport infrastructure, including roads and ports, which are also supported by governmental schemes, are generally well developed, even if the countries are not at the same level of economic performance.

However, to date, SADC industrial policies and strategies have not contributed significantly to the development of industry in the region. There is need therefore to ensure a balanced and mutually beneficial industrialization in the region with focus on the promotion of productive industrial linkages and efficient utilisation of regional resources for the creation of productive employment opportunities across the region.

      - Weaknesses and challenges

Despite all the above, economic and industrial development of the region is limited by numerous factors at the macro, sectoral and micro levels. Across the region these problems mainly converge to the common industrial scenario, where:

- most of the mineral, agricultural and fish production manufactured in the region is still exported in a primary or unfinished form. About 90% of SADC exports comprise of mineral and agricultural goods and its imports are mainly capital and intermediate goods. Only the Republic of South Africa and to some limited extent Zimbabwe have the capacity to produce capital and intermediate goods. This impacts negatively on the development of the region and leads to imbalances in economic levels. There is need to further process the primary goods to add value, increase employment levels and increase the contribution of locally produced goods to the regional economy;

- small size of local markets and low purchasing power inhibit economies of scale. Political instability in some SADC countries, growing informal sector and poverty level predetermine narrow market for industrial goods;

- escalating costs of raw materials, labour and other inputs, including energy and other utilities, threaten companies’ financial viability;

- poor infrastructure networks (roads, rail and inland river transport) work against exporters as well as importers. Even in South Africa, the region’s number-one economy, infrastructure represents a bottleneck for industrial development;

- limited access to medium and long term capital and funding. SMEs are frequently complaining of a lack of development finance, absence of long-term capital for industrial development and insufficient resources. Bank credit is not easily accessible, especially to SMEs;

- high dependence on imports as regards inputs, including equipment and high duties on imported materials. Due to shortage of foreign currency, enterprises find difficult to import raw materials and execute their export contracts. The region is highly dependent on imported goods, mainly from South Africa;

- currently overvalued exchange rate in some Member States puts most companies operating internationally under extreme pressure. It has become 30% more expensive to produce in Swaziland, while China has become 20% cheaper than average world conditions. In Zimbabwe, the hyper inflationary rate has nearly destroyed the monetary system;

- legal and regulatory obstacles for business together with high fiscal pressure. There is a long turn-around time in company registration and obtaining industrial and trading licenses. Procedures for intra regional or international trading generally take a long time, which is a negative factor of the regional competitiveness (see Chart 8);

- inadequate institutional and technical support infrastructure characterize existing industrial support services. Public or private institutions supporting industry (e.g. technical centres, chambers of commerce and industry, professional associations, employers associations, consultants associations) often lack adequate human and financial resources, institutional capacity and necessary equipment;

- nearly non-existent conformity and quality infrastructure which excludes the big part of the region’s production from the world market. Manufacturing companies operating, in particular, in the agro-processing sector and marketing their production internationally experience difficulties in maintaining the necessary quality level and conformity to internationally accepted standards and norms (SPS, ISO management systems);

- lack for internationally recognised accreditation due to use of poor and obsolete technologies and poor packaging practices;

- lack of qualified personnel and poor corporate governance represent a great challenge for industrial growth and further development of the private sector. The low capacity of professional training and business advisory institutions are one the key reasons for the low productive performance of local companies. There is, hence, a strong need to strengthen capacities and provide institutional support to consulting and professional training institutions;

- in order to sustain an environmentally friendly industry, there is need to introduce measures aimed at safeguarding the adverse impact of industrial operations on the environment.

Chart 8:

Trading Across Boarder - Time for Export/Imports (Days), 2006

Source: African Development Bank

The industrial sectors in the region need to withstand the challenges of globalisation, which range from competitiveness to industrial and product diversification, productivity, technology transfer and research and development. This can only be achieved with an overall improvement in productivity and competitiveness combined with a diversified and balanced industrial growth in a wider, well-linked economic space that allows for the efficient and effective use of factors of production on the basis of increased value addition.

SADC should pay particular attention to investment promotion, entrepreneurship development and ensuring that the manufactured products meet internationally recognised standards and quality in order to compete favourably in the global economy. In this regard, the upgrading of national and regional institutions providing technical assistance to the industrial sectors is particularly critical for value addition.

The challenges in the manufacturing sector include the acquisition of environmentally friendly industrial technologies and know how to ensure sustainable development in the region.

  - Factor costs and competitiveness of manufacturing sector

Development of infrastructure and services is critical for promoting and sustaining regional industrialization, trade and investment growth. The potential for deepening integration through sharing of production, management and operations of infrastructure facilities, hubs, development corridors or poles is considerable.

While the overall picture in SADC is one of inadequate coverage, poor maintenance, weak financing and inefficient management systems, differences do exist across the Member States. Many countries have been able to upgrade and expand their infrastructure assets and improve services through a combination of policy changes, institutional reforms and favourable investment climate. These policy reforms have paved the way for increased private sector involvement in the provision of infrastructure resulting in commercialisation and cost recovery measures being put in place. The major challenge now facing Governments is to establish regulatory frameworks to foster fair competition, support the emergence of a regional market and ensure that end users obtain the expected benefits.

In order to enable the region to meet the challenges of infrastructure development, SADC has put in place legal and policy frameworks through the formulation and adoption of appropriate instruments such as protocols and policy and strategy guidelines.

Table 9:

Access to the Basic Infrastructure Services, 2000-2004

|  | Access to electricity |  |  |  | Water supply coverage (%) |
| --- | --- | --- | --- | --- | --- |
|  | Final consumption (GWh) |  | Distribution losses (GWh) |  |  |
|  | 2000 | 2004 | 2000 | 2004 | 2004 |
| Angola | 1 157 | 1 799 | 211 | 325 | 53 |
| Botswana | 1 959 | 2 041 | 164 | 131 | 95 |
| DRC | 2 442 | 2 254 | 228 | 211 | 22 |
| Lesotho | … | … | … | … | 79 |
| Madagascar | … | … | … | … | 31 |
| Malawi | … | … | … | … | 67 |
| Mauritius | … | … | … | … | 100 |
| Mozambique | 1 013 | 7 019 | 243 | 1 187 | 40 |
| Namibia | 2 386 | 2 790 | 260 | 304 | 87 |
| Seychelles | … | … | … | … | 88 |
| South Africa | 162 516 | 197 497 | 17 053 | 14 710 | 88 |
| Swaziland | … | … | … | … | 62 |
| Tanzania | 1 913 | 1 927 | 555 | 578 | 52 |
| Zambia | 6 039 | 7 712 | 249 | 338 | 62 |
| Zimbabwe | 10 494 | 10 117 | 1 422 | 1 472 | 81 |
| AFRICA | 345789 | 431683 | 53377 | 59758 | 62 |

Sources: 	Electricity: IEA - online database, 2006; Water supply coverage and sanitation coverage: WHO and UNICEF, 2006.

Tables 10 and 11 give comparative analysis of the prices on basic production utilities and transaction costs in some SADC and OECD Members States, as well as throughout the African Continent.

Table 10:

Production Utility Costs, 2005

|  | Telecom Costs (USD/ minute) |  |  | Internet costs | Electricity costs |  | Water costs |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Local calls | International call to adjacent country | International call to the USA | High bandwidth Internet (USD/ mo.) | Usage charge for industrial use (USD/kWh) | Demand charge for indust-rial use (USD/kVA) | Water for industrial use (USD/m³) |
| Lesotho | 0.33 | 0.36 | 1.08 | 814 | 0.04 | 7.07 | 0.49 |
| Madagascar | 0.08 | 0.75 | 0.90 | 840 | 0.08 | 12.02 | 0.26 |
| Mauritius | 0.03 | 0.19 | 0.19 | 188 | 0.06 | 3.25 | 0.38 |
| Mozambique | 0.06 | 0.42 | 0.77 | 594 | 0.05 | 5.25 | 0.88 |
| South Africa | 0.06 | 0.26 | 0.54 | 42 | 0.08 | 0.88 | 1.38 |
| Tanzania | 0.07 | 0.47 | 1.11 | 1900 | 0.06 | 6.01 | 0.67 |
| Comparator country |  |  |  |  |  |  |  |
| Tunisia | 0.01 | 0.48 | 0.52 | 18 | 0.07 | 1.48 | 0.68 |
| France | 0.02 | 0.17 | 0.17 | 34 | 0.07 | n/a | 1.99 |
| Ireland | 0.05 | 0.15 | 0.19 | 43 | 0.12 | 8.70 | 1.63 |
| Ghana | 0.02 | 0.28 | 0.39 | 252 | 0.05 | 12.29 | 0.77 |
| Kenya | 0.04 | 0.16 | 0.88 | 1690 | 0.06 | 3.68 | 0.42 |
| Mali | 0.03 | 0.59 | 0.89 | 1089 | 0.12 | 2.91 | 0.56 |
| Senegal | 0.23 | 1.07 | 1.07 | 57 | 0.14 | 13.10 | 1.56 |
| Nigeria | 0.16 | 0.43 | 1.45 | 236 | 0.28 | n/a | 0.91 |
| Uganda | 0.07 | 0.38 | 0.76 | 3548 | 0.10 | 2.33 | 0.76 |

Source: Snapshot Africa (2007), World Bank

Table 11:

International Sea Freight Rates (USD Per 40 foot container)

| Container Type | To Rotterdam |  | To New York |  | To Long Beach |  | To Yokohama |  | To Singapore |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Standard | Refrigerated | Standard | Refrigerated | Standard | Refrigerated | Standard | Refrigerated | Standard | Refrigerated |
| Lesotho | 1450 | 2900 | 3500 | 7000 | 3700 | 7000 | 1250 | 2500 | 1100 | 2000 |
| Madagascar | 1948 | 5948 | 5445 | None | 5755 | None | 2484 | 5084 | 1684 | 5284 |
| Mauritius | 1161 | 1161 | 5050 | 5050 | 5815 | 5815 | n/a | n/a | n/a | n/a |
| Mozambique | 3123 | 4842 | 4621 | 5146 | 5071 | 6546 | 2131 | 5456 | 1731 | 5256 |
| South Africa | 2606 | 3750 | 3540 | 4405 | 3850 | 5500 | 1700 | 3600 | 1500 | 3000 |
| Tanzania | 1118 | 2118 | 4286 | 6786 | 4350 | 6900 | n/a | n/a | n/a | n/a |
| Comparator country |  |  |  |  |  |  |  |  |  |  |
| Tunisia | 2000 | 5475 | 4900 | 5675 | 5400 | 7075 | 2200 | 6275 | 1400 | 6075 |
| France | 3111 | 2940 | 4552 | 7975 | 5600 | 4775 | 2852 | 5800 | 1700 | 4800 |
| Ireland | 3500 | 6500 | 6800 | 8400 | 7000 | 8800 | 3500 | 4500 | 3500 | 4500 |
| Ghana | 1953 | 4948 | 3500 | 4500 | 2900 | 4200 | 3500 | 4500 | 3500 | 2600 |
| Kenya | 3800 | 9500 | 3800 | 10691 | 4100 | 10691 | 3200 | 10691 | 3000 | 10491 |
| Mali | 4392 | 5218 | 6926 | 7754 | 8525 | 9377 | 4703 | 7168 | 4393 | 7061 |
| Senegal | 2193 | 4239 | 4500 | 5902 | 6477 | 9362 | 2431 | 6706 | 2106 | 6206 |
| Nigeria | 2161 | 3824 | 4756 | 7256 | 5456 | 7956 | n/a | n/a | n/a | n/a |
| Uganda | 1097 | 1097 | 2891 | 2891 | n/a | n/a | n/a | n/a | n/a | n/a |

Source: Snapshot Africa (2007), World Bank

The general picture of competitiveness indicators in SADC countries could be summarized in the following table, where the Sectoral Effect Indicator reflects the contribution to a country’s export growth and the Global Competitiveness Effect, or the balance (export growth minus world growth and sector effect), measures the contribution of changes in sectoral market shares to a country’s export growth.

Table 12:

Competitiveness Indicator in SADC Member States, 2000-2005

|  | Sectoral effect | Global competitiveness effect |
| --- | --- | --- |
| Angola | 13.5 | 23.4 |
| Botswana | 9.7 | 488.1 |
| DRC | 5.8 | -16.4 |
| Lesotho | -10.2 | 26.1 |
| Madagascar | -8.7 | -5.4 |
| Malawi | -11.9 | 3.5 |
| Mauritius | -5.6 | -7.2 |
| Mozambique | -4.1 | 18.9 |
| Namibia | -0.8 | 60.2 |
| Seychelles | -5.3 | 8.5 |
| South Africa | 2.1 | -5.0 |
| Swaziland | -5.9 | 20.2 |
| Tanzania | -2.5 | 9.5 |
| Zambia | 7.3 | 11.2 |
| Zimbabwe | -2.5 | -11.6 |
| AFRICA | 4.5 | 2.8 |

Source: PC-TAS 2001-2005 International Trade Center UNCTAD/WTO.

Summarizing the overall picture of competitiveness in SADC countries we refer to the World Bank’s Doing Business indicators in the table below where all 15 Member States of the region are classified in decreasing order according to the cumulative business climate indicator.

Table 13:

World Bank’s 2008 Doing Business Ranking

|  | Mauritius | South Africa | Botswana | Namibia | Zambia | Seychelles | Swaziland | Lesotho | Tanzania | Malawi | Mozambique | Madagascar | Zimbabwe | Angola | DR Congo |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ease of Doing Business | 24 | 32 | 38 | 51 | 100 | 104 | 108 | 123 | 127 | 134 | 141 | 144 | 158 | 168 | 181 |
| Starting a Business | 7 | 47 | 80 | 112 | 71 | 68 | 153 | 125 | 109 | 122 | 144 | 58 | 164 | 156 | 154 |
| Dealing with Licenses | 36 | 48 | 119 | 38 | 146 | 56 | 21 | 150 | 172 | 156 | 153 | 102 | 174 | 125 | 141 |
| Employing Workers | 64 | 102 | 73 | 34 | 135 | 120 | 40 | 63 | 140 | 96 | 161 | 153 | 127 | 174 | 175 |
| Registering Property | 127 | 87 | 29 | 129 | 91 | 55 | 153 | 135 | 142 | 96 | 149 | 145 | 85 | 173 | 152 |
| Getting Credit | 84 | 2 | 43 | 12 | 68 | 163 | 43 | 84 | 84 | 84 | 123 | 172 | 84 | 84 | 163 |
| Protecting Investors | 11 | 9 | 38 | 70 | 70 | 53 | 178 | 142 | 88 | 70 | 38 | 53 | 113 | 53 | 150 |
| Paying Taxes | 11 | 23 | 17 | 96 | 38 | 40 | 52 | 54 | 109 | 58 | 88 | 92 | 157 | 130 | 153 |
| Trading Across Borders | 20 | 147 | 149 | 150 | 153 | 90 | 154 | 141 | 103 | 167 | 140 | 109 | 162 | 172 | 160 |
| Enforcing Contracts | 76 | 82 | 92 | 36 | 87 | 62 | 129 | 104 | 33 | 138 | 124 | 153 | 77 | 179 | 173 |
| Closing a Business | 70 | 73 | 26 | 52 | 80 | 181 | 65 | 69 | 111 | 135 | 133 | 181 | 154 | 142 | 150 |

Source: World Bank Doing Business 2009 Report

  - Technical support institutions

Existing institutions providing technical support for industries in SADC countries can be generally classified in following categories:

- Ministries of Industry and/or Trade and their departments;

- Investment and Export promotion agencies;

- Chambers of Commerce, Industry and Agriculture or other agencies in charge with SMEs;

- Agencies in charge of SME development;

- Professional associations;

- Consultants associations;

- Technical centres;

- Development banks, financial institutions and funds.

Institutional background, scope of activities and support capacities of such institutions vary from one country to another. In some cases sectoral and assistance mandates are overlapped by different public and private institutions, several departments within one ministry or general directorate. This often results in either a lack of or ineffective coordination and common approach in bringing technical support to the local operators. It largely explains the absence of effective mechanisms of investments and export promotion at regional level.

Concerned ministries or other official bodies are not independent enough to build their own development and support strategies as linked with political decisions.  As a result there is a shortage in institutional cooperation and experience exchange with international and foreign partner organisations.

Regarding the Chambers of Commerce and Industry and other sectoral or professional associations of non-governmental sector, since they are mainly self-supporting or funded by members - mostly small and medium enterprises, such support institutions are usually limited in human and financial resources, although strongly committed to deliver support services and build public-private partnership.

The consultants associations are facing the following major obstacles: the SMEs cannot afford consultants services even if subsidized; enterprises are seeking for assistance from international donors to cover consultants’ fees; the larger enterprises prefer to appeal to international consultant firms. In most cases, the companies encounter difficulties in implementing consultants’ recommendations due to the lack of internal capacities, as such services as coaching and follow-up are usually neglected.

Development banks, financial institutions and funds as Development Bank of Southern Africa (DBSA) located in South Africa or SADC Development Finance Resource Centre with headquarters in Botswana, in the limits of their mandate, are called to bring indirect assistance mostly through providing financial support to development activities in the framework of thematic programmes and initiatives.

The national Centers of Technical Support to industries carry tremendous potential in providing direct and most tangible assistance to the local producers and exporters. Such large sectoral centers as Grain SA or the Citrus Growers Association of South Africa hold technical support portfolio comparable with services offered by professional organizations in developed countries. They could serve as models to develop or establish industrial support network throughout the SADC region.

At regional level some centers represent a strong force in achieving SADC regional objectives of trade facilitation and exports growth. Examples of existing regional sectoral centers include:

- Council for Scientific and Industrial Research (CSIR), based in South Africa;

- MINTEK, South Africa;

- Southern and Eastern African Minerals Centre (SEAMIC,) Tanzania;

- Mauritius Sugar Industry Research Institute (MSIRI), Mauritius.

Well structured and possessing considerable human and institutional capacities, these centers benefit from intensive international cooperation and remain up-dated in terms of methods and technologies applied.

The existing national technical support centres in SADC are as listed in Annex VI.

In most of the developed and developing countries, technical centres and so-called “Business Development Services” (BDSs) play an important role in supporting industrial enterprises and related services.  Such technical support institutions can provide the following services.

Diagram 1:

##### Typical services provided by the technical support centers

| MONITORING & FOLLOW-UP |  | TECHNICAL ASSISTANCE |
| --- | --- | --- |
| Patents Pre-normalization, national & regional regulation Environment, sustainable development Product safety, consumer protection, security at civil works |  | Testing, Measuring, Analyses Platform and on-site evaluations Consultations, Audit and Expertise |
| RESEARCH & DEVELOPMENT |  | TECHNICAL EXPERTISE |
| Inputs, production, process Calculation methods and tools Quality security Methods, techniques and platform for testing Methodologies for feasibility studies |  | Consulting and audit: standardization, regulations Occupational safety Environmental assessment Energy efficiency |
| PARTNERSHIP |  | INFORMATION AND TRAINING |
| Project design and management in cooperation with: Companies and associations Regions Public research centres |  | Media, dissemination activities, forums Professional training for companies Training programmes for high and secondary education institutions |

  - EPA impact analyses

Historically, progress towards harmonised and integrated sub-regional markets amongst ACP countries has been slow and difficult. Regional institutions and secretariats have lacked financial and technical resources to supervise and coordinate cooperation, and the political will to implement decisions. EPAs have a legal obligation to support and strengthen regional integration which would provide benefits to ACP countries through the pooling of resources, the expansion of markets, increased trade and investment, and greater diversification and value addition.

Moreover, given the historical experience and the financial and technical capacity of the EU, EPAs also offer great scope for cooperation in regard to inter-regional cooperation. EPAs could provide the opportunity to create a more credible and rationalised system of supra-regional integration between different regional groupings throughout Africa, in line with, for instance, the African Union agenda for the rationalisation and coordination of African RECs.

Some studies have been undertaken to assess the possible impact of EPA on regional integration within SADC and on national economies in particular. However their results and estimations vary from one study to another. The major outputs of conducted analyses could be summarised in following recommendations addressing regional and national dimensions:

- To strengthen capacities of political institutions (national governments, at SADC extent),

- To support economies, their priority and contributing sectors,

- To develop exports in order to maximise the benefits from liberalised access to European markets,

- To exclude some non-competitive products and diversify industrial pattern and the rhythm of openness of regional market,

- To compensate the losses in customs revenue,

- To negotiate trade issues leading to development of agricultural and export sectors.

  - Financial mechanisms

      - Current situation in private sector financing

Foreign Direct Investments (FDI) are a central determinant of the rate and pattern of economic growth in SADC economies. By increasing external capital flow and using the resources in productive domestic investment, SADC economies intends to strengthen the region's prospects for accelerated economic growth, poverty eradication and sustainable development.

In 2001, the average SADC Gross Domestic Capital Formation (GDCF) was 16.8% of GDP. Among individual countries, there were wide disparities in foreign investment rates, with most countries recording low DI flow.

As far as FDI is concerned, SADC as a Community attracted on average only US$ 691 million in the early 1990s, but FDI to the region quadrupled in the second half of the 1990s standing on average at US$ 3061 million during 1995-98. This figure accounts for more than half (55%) of all FDI flows directed to Sub-Saharan Africa.

Southern Africa has emerged as a strong pole for attracting foreign investment to Sub-Saharan Africa (SSA). From 1995 to date, more than 25% of FDI to Sub-Saharan Africa region were directed to Southern Africa. Individual SADC countries appear to have performed relatively well compared with other Sub-Saharan countries. For example, six SADC Member States (South Africa, Angola, Zambia, Lesotho, Tanzania and Namibia) were among the top 10 recipients of FDI in Sub-Saharan Africa during the second half of the 1990s.

The outlook for investment in SADC would not be complete without bringing the cross-border regional dimension into the picture. South Africa, Mauritius and Zimbabwe are the main sources of cross-border investment into other SADC countries. Currently, intra-regional investments in the SADC-region are concentrated in the following sectors: mining, tourism, transport, finance, manufacturing, retail, telecommunications, agriculture and fisheries.

The main avenues for FDI in SADC are privatisation and public-private provision of infrastructural services. Most countries are also attracting resource-seeking foreign investment flows. In general, efficiency and market-seeking investment flows remain proportionately small.

A number of regional and international financial institutions and development agencies like KFW, GTZ, Agence Française de Développement, Danida, European Investment Bank are currently developing or implementing programmes to facilitate the private sector’s access to funding through development of local commercial banking infrastructure.  Participation of the local commercial banks in companies financing is crucial for different reasons:

- the banks are called to exclude insolvent and other ‘doubtful’ companies at the very early stage of selection process;

- the banks will largely contribute to effective financial monitoring and follow-up of Programme implementation;

- the banks could serve as sustainable source for funding going beyond the limits and goals fixed by the Programme. They can participate at funding the lease or purchase of complementary equipment.

Meanwhile, the banking sector in the SADC countries is generally weak and does not provide the local operators with internal funds sufficient to meet domestic financing needs for economic growth.

In addition, the regulatory constraints of national monetary policies do not allow the banks to transform their liquidity. There are only a few financial products available and the financial institutions that would be able to offer diverse financial products are either non-existent or offer a limited service portfolio. In most SADC countries, the interest rates are high, which discourages demand for loans.

Having the credit level below the current needs in investments, the local enterprises do not benefit from long-term funding and, as result, depend mostly on auto-financing.

Other problems resulting from the poor performance of the financial sector in SADC countries include number/volume of financial transactions being undertaken outside the formal banking sector and the scarcity and high costs of such transactions.

Due to these constraints, it is suggested that the current Programme uses the following financial mechanisms.

      - The Regional Industrial Development Fund

A Regional Industrial Development Fund has been proposed as a tool to finance industrial development programmes through mobilizing and coordinating development partners’ contributions. Inter alia, the Regional Fund is expected to finance initiatives aimed at upgrading and improving competitiveness of industries.

Financial resources of Regional Industrial Development Fund are envisaged to originate from various sources, including the followings:

- SADC funds;

- Regional financial institutions (African Development Bank, Development Bank of Southern Africa, Industrial Development Corporation, PTA Bank, etc.);

- International Financial Institutions (World Bank, International Finance Corporation, European Investment Bank, Islamic Development Bank, OPEP Fund, etc.);

- European Community with Contribution Agreement;

- EU Member States;

- Other development partners (USA, China, Canada, etc.);

- Members of the African Diaspora;

- Benevolent donors/organizations.

The Fund will operate at regional and national levels. The SADC Secretariat must ensure the synergy between diverse sources of funding and the Regional Industrial Development Fund.

Predetermined scope of the Regional Fund’s activities makes the latter the principal funding source for the current Programme implementation at regional level.

      - Schemes and mechanisms for funding upgrading and competitiveness

Within the Pilot Phase of the Programme implementation, it is also proposed to undertake feasibility study on establishment of the national financial mechanisms for funding of upgrading programmes in every Member State. The results of this study will determine the needs in upgrading of existing national mechanisms or establishment of the new ones. The study will also fix the number of such units to be created in each country. For example, Tunisia, which has already successfully implemented the national upgrading programme, had decided to create a unique national fund.

The financing of these mechanisms could be provided through the governmental allowances, transfers from the Regional Industrial Development Fund, regional and international financial institutions, the EC and EU Member States in the framework of bilateral cooperation, European Investment Bank and other development partners (governments of USA, China, Canada, etc.).

The main purpose of the national mechanisms is to cover financial costs of upgrading and modernization actions mainly related to initial assessment, design and implementation of related activities. All investments associated with upgrading and modernization plans that meet eligibility criteria will also be considered for funding. Some of such activities could include:

- purchase and delivery of equipment (manufacturing equipment, tools, machinery and spare parts);

- engineering works,

- equipment installation,

- recruitment and training,

- implementation of management systems,

- feasibility studies and business plans,

- market studies.

Unless the national regulations provide compensations, certain costs will not be covered, notably:

- repayment of debts;

- covering loan interests and provisions;

- costs already financed by other sources;

- purchase of realty (land parcels or buildings) unless the latter is indispensable for companies’ operations;

- covering different fiscal fees and taxes, VAT…

- CONTEXT AND JUSTIFICATION OF THE PROGRAMME

  - SADC: Background, Strategy, Priorities and Challenges

      - SADC Regional Integration Process

Established in 1992 and originated from the Southern Africa Development Coordination Conference (SADCC), the Southern African Development Community is pursuing intra-regional trade integration, forming a free trade area (FTA), with the ambition of moving towards a customs union. In parallel, several SADC members are involved in negotiations with other regional organizations.

Initially SADC was seen as a vehicle for political integration. This political platform, which is still SADC’s strong suit, then took on trade matters. The SADC Trade Protocol was adopted in 1996 and came into force in September 2000. It envisions the formation of an FTA, with liberalization of 85% of all intra-regional SADC trade by 2008.

During the transition period towards the FTA, SADC countries may trade on preferential terms in an asymmetrical manner. Under these arrangements, South Africa (and indirectly its customs union partners Botswana, Lesotho, Namibia, Swaziland) is expected to open its market faster than the other SADC members. Although the trade protocol does not mention a customs union, there has been a proposal for the formation of a SADC customs union by 2010 and a common market by 2015.

The SADC Trade Protocol contains provisions not only on market access for goods, but also arrangements for rules of origin, Technical Barriers to Trade (TBT), and Sanitary and Phytosanitary (SPS) measures. The protocol also promotes cross-border investment and future trade liberalization in services.

All indicators suggest that the SADC countries as well as the SADC region as a whole have increased their openness. However, trade flows among SADC countries are still relatively low. During the 1990s, SADC intra-regional trade as a percentage of total trade more than doubled, reaching 20% in 1997. The overall figure for intra-regional trade stood at roughly 25% by 2003. These figures however take South Africa into account. South Africa experienced a disproportional increase in trade after the change of political regime in 1994 and now accounts for over 70% of intra-SADC exports, enjoying a large trade surplus with the other members.

In spite of the SADC Trade Protocol’s ambitious agenda, limited progress has been made in regional economic integration. The trade policy of several SADC members has not been consistent with their tariff reduction schedules. Furthermore, some of the most important product lines have been excluded from liberalization. The volume of goods that SADC countries wish to leave out of any regional liberalization is also worth more than the agreed 15%.

It is important to note that most SADC members belong to at least one other regional grouping. This is perfectly consistent with the principles of an FTA, where each member remains in charge of its own trade policy towards non-members. A country can thus belong to several different FTAs, as is often the case. However, in the case of customs unions, where members adopt a common external tariff and policy, a lack of coherence leads to conflicting obligations.

A sub-group of SADC members, South Africa and the BLNS (Botswana, Lesotho, Namibia and Swaziland) countries, have formed the Southern African Customs Union. A possible SADC customs union will thus require alignment with the SACU common external tariff. To complicate matters further, several SADC members also belong to the Common Market of Eastern and Southern Africa (COMESA), which is set to become a customs union by December 2008. Also, Tanzania, in addition to its SADC membership, is also part of the East African Community (EAC), which became a customs union in 2005, but the country is not a COMESA member, like its two EAC partners, Kenya and Uganda (see Figure 1, page 15). This has led to unavoidable conflicting economic integration commitments and objectives.

Besides the lack of harmonized inter- and intraregional trade policies, there has been little progress in formulating a coherent trade policy among SADC members, despite the SADC Trade Protocol.

All SADC countries are members of the World Trade Organization (WTO) and participate in the Doha Development Round. They are also signatories to the Cotonou Partnership Agreement and are thus currently negotiating an EPA with the European Union. The exception is South Africa, which, as a “qualified” member only under the ACP-EU partnership agreement, does not benefit from the EU non-reciprocal trade preferences. Instead, it has concluded an FTA with the European Union. This Trade, Development and Cooperation Agreement (TDCA), has been in force, provisionally and partially since January 2000 and fully since May 2004. Besides, SADC members take part in bilateral agreements with one another and with other countries. Several SADC countries benefit from preferential market access to the United States under the African Growth and Opportunity Act (AGOA). SACU is also negotiating a possible free trade agreement with the United States, and one with MERCOSUR, and a future trade agreement with India is also possible.

      - Regional development strategies and objectives

In SADC, industrialization has been pursued vigorously through various policies and programmes, with various objectives such as import substitution, employment creation and export promotion, with varying degrees of success.

The SADC Regional Indicative Strategic Development Plan (RISDP)

Approved by the SADC Council of Ministers at their meeting in Dar Es Salaam, Tanzania, in August 2003 and launched in March 2004, the SADC Regional Indicative Strategic Development Plan (RISDP) focuses on promoting trade, economic liberalization and development as a means of facilitating trade and financial liberalization, competitive and diversified industrial development and increased investment.

In order to attain this goal, RISDP is pursuing, inter alia, competitiveness enhancement through:

- industrial development and increased productivity in all sectors;

- private sector development;

- diversification of regional economies;

- trade liberalization and development;

- liberalization of factors of production;

- research science and technology innovation, development and diffusion;

- enabling institutional environment for technical support.

Following several meetings at both Regional and Sub-regional levels, the SADC Ministers of Industry and Trade adopted a methodology based on the value chain (global/local) of specific industry categories in order to identify priority segments where comparative advantage exists, so as to make specific and appropriate interventions.

The following 9 strategic sectors were selected as those offering the most global comparative advantage and growth potential:

- Agro-food;

- Processing of Minerals (metallic and non-metallic) products;

- Leather and Leather products;

- Forestry;

- Fisheries;

- Chemicals, Petroleum and Pharmaceuticals;

- Textiles and Garments;

- Machinery and Equipment; and

- Services.

The SADC Ministers of Industry and Trade decided that strategies and action plans should be developed, with the assistance of UNIDO, at both the SADC Regional level and national levels to improve industrialization and promote employment in the SADC region.

The SADC Regional Road Map

At the request of SADC Secretariat, UNIDO undertook a survey to assist in value chain studies for two out of three priority sectors in each SADC Member State. With financial support from South Africa, Regional Strategies and Action Plans for all the nine priority sectors were developed. The latter were aggregated and adopted by the recent Inaugural Meeting of SADC Industrial Development Forum (7-8 June 2007) as the SADC Regional Road Map.

This document provides the detailed plan of actions to be taken at the regional level in the three top-priority sectors, namely: agro-food processing, minerals (metallic and non-metallic) processing and pharmaceuticals.

The following is a brief summary of the relevant actions recommended by the Regional Road Map for the three priority sectors:

- Agro-food processing

  - SME Development

Recommended actions:

    - There is need to develop an SME programme with emphasis on Women in food processing industry as well as a special programme for the people who are physically challenge. This reflects the fact that agro-processing industry has more women players; particular emphasis should be placed on enhancing their skills capacity and income.

    - Undertake entrepreneurship development and capacity-building in agro-food sector.

    - Establish agro-food processing related skills development programmes to promote technology, technical skills acquisition and technology diffusion.

  - Undertaking integrated infrastructure development

Recommended actions:

    - Physical infrastructure projects should be linked with each other. For example, the ports should be linked with the rail networks, which should also lead to the industrial estates and sources of agro-food raw material

    - The existing physical infrastructure should be revamped to reduce turnaround time and reduce transportation and logistics costs in SADC.

    - Develop of industrial clusters and encourage collaboration among the members.

    - Communication, energy supply, water and other infrastructure and technology should be provided and linked to these industrial clusters.

  - Developing market access

Recommended actions:

    - Develop quality infrastructure (through SQAM - conformity, mutual recognition, equivalence and confidence building; Sanitary and Phytosanitary Systems) and promote compliance with quality standards.

    - SADC Member States should address the Technical Regulations and Technical Barriers to Trade (TBTs); they should accelerate the reduction and eventual total removal of all tariffs/ NTBs in this sector within SADC.

    - Encouraging producers to improve packaging, distribution and marketing of their products.

    - With regard to global markets, Member States should assist private sector companies to participate in international trade fairs in order to promote their products.

    - Business delegations should visit target markets to promote their products.

    - Strategic alliances should be encourage between local companies and foreign companies in the value chain.

  - Development/management of water resources

Recommended actions:

    - Address shortage of water in the region by establish of a regional water commission for river basins in line with the SADC Protocol on Shared Water Courses.

    - Improve management of the Regional shared water resources.

    - Ministers of Industry should discuss this with the Ministers responsible for Water.

  - Improving the industrial governance

Recommended actions:

    - Harmonization strategies and policies on agro-processing sector

    - Involve Sector Associations and Trade Unions in decision-making on the agro-food sector

    - Establish Performance Monitoring Committee at both regional and national levels. Membership of this committee should be competitive and must be paid in order to attract high-calibre people. Individuals with technical and managerial expertise should be headhunted to serve on this committee.

  - Provision of industrial and market-sensitive information

Recommended actions:

    - Facilitate the gathering and dissemination of technical and marketing information and knowledge on the agro-food sector, through regional and national centres.

    - Promote networking and backward linkages (through Joint Ventures) among private sector stakeholders in agro-food sector.

    - Improve capacity of Statistics Unit of SADC Secretariat to collate industrial statistics. National Statistics Offices should be obliged to provide current industrial statistics on time to this unit.

    - Promoting positive media reporting about Africa.

    - Develop a regional data bank for equipment and machinery suppliers and disseminate information on their products.

  - Improving Research and Development

Recommended actions:

    - Increasing investment in R&D.

    - Provide of proactive incentives favoring agro-food processing sector.

    - Undertake an assessment of the identified Centres of Excellence and provide support for any weaknesses identified.

    - Promote and rewarding innovation.

- Minerals processing

Recommended actions:

- Enhance and broaden the skills base.

This should involve:

- regional collaboration in HRD (especially at the technicians and engineers level);

- address the bottle-necks in the HRD pipeline (especially in mathematics and science);

- harmonizing HRD accreditation systems in Member States;

- assessing regional HRD capacity to produce requisite skills for value-addition;

- addressing the HIV/AIDS pandemic to minimise its impact on skills availability.

- Promote beneficiation of minerals and scrap metals.

- Increase investment in and coordination of R&D.

- Forster innovation (i.e. promote and reward innovation).

- Develop vibrant and competitive downstream manufacturing industries (mostly SMEs).

In that regard, Member States should re-negotiate any current agreements with the main mining companies in order to ensure buy-in.

- Develop strong foundry industry (1st Stage in beneficiation chain);

- Develop of industrial clusters; promote networking and collaboration;

- Subsidize electricity cost to downstream producers;

- Provide coordinated technical support services;

- Improve technological capabilities of downstream industries (fundamental to increasing competitiveness);

- Assist firms to upgrade equipment/Invest in new technologies.

- Translate existing linkages into joint growth and development.

- Precious Metals and Minerals

- Establish requisite refining capacity;

- Establish semis production capacity;

- Assess regional design and marketing collaboration.

- Market Access (Trade Barriers; NTBs).

- Marketing (Pricing; Margins; Promotions).

- Involve Sector Associations and Trade Unions in decision-making.

- Centres of Excellence

Centres of Excellence should be identified and assisted to play their role in improving industrial performance. Such centres should be at both regional and national levels.

        - Regional Centres of Excellence, e.g.

- SEAMIC, Tanzania;

- Mintek;

- CSIR.

        - National Centres of Excellence, e.g.

- Assess capacities and capabilities to play roles;

- Improve capacities and capabilities.

- Enhance collaboration between Regional and/or National Centres of Excellence & Industry players (e.g. Project AuTek between Mintek and AngloGold).

- Establish Agency for Registering Patent Rights.

- Regulatory Environment and Cost of doing business.

- HIV/Aids.

- Promote positive media reporting about Africa.

- Infrastructure development: Without the infrastructure in place, becoming competitive will only remain a dream.

- Pharmaceuticals

Recommended actions:

- Collaborate to develop a regional chain for the pharmaceutical industry

- Undertake detailed study of pharmaceuticals industry in Angola, DRC, Lesotho, Madagascar, Mauritius, Mozambique, Namibia, South Africa, Tanzania, Zambia and Zimbabwe (May 2007).

- To facilitate the above process, there is need to establish technical working committee whose mandate would be to set up the modalities for the development of the pharmaceuticals sector in SADC (April 2007).

- Explore the possibility of integration of indigenous herbal and traditional knowledge and practices into the healthcare industry.

- The SADC pharmaceuticals industry must aspire to be U.S. FDA and European Medical Evaluation Agency (EMEA) compliant in order to harness the growth opportunities in areas of contract manufacturing and research.

- A study should be undertaken to assess the quality of drugs from India. This is to prevent dumping of low quality drugs onto the market in SADC (June 2007).

- Develop internships and mentoring programmes to close the gaps in technical skills. In that regard, there is need for collaboration between government, the private sector and academia to build capacity for quality analysis.

- Establish an Africa-wide Medical Evaluation Agency, with the power to grant drug approval for the continent. In doing so, there is need to explore the Chinese model of healthcare provision so that SADC can understand out how China managed to provide pharmaceutical products and healthcare services to its large population without depending on the West countries. SADC can also learn from Algeria’s pharmaceuticals industry (July 2008).

- Shift the focus of the industry from being research/supply driven to being commercial/demand driven.

- For a start, concentrate on the development of generic drugs (tablets, injections and liquid formulations), and the assembly of medical equipments and instruments.

- Improve distribution throughout SADC and internationally.

- Pharmaceutical companies to invest heavily in R&D. A significant increase in the level of funding is required.

- Establish duty-free pharmaceutical zones, with attractive incentives, in Angola, DRC, Lesotho, Madagascar, Mauritius, Namibia, South Africa, Tanzania, Zambia and Zimbabwe. A reduction in restriction, such as exchange controls, would also encourage foreign investment in the local industry.

- Research and develop the use of locally available raw materials and local knowledge.

- Certain parts of the value chain should be located in SADC member states where there is comparative advantage.

- Member States should create the appropriate regulatory environment for developing the sector to become commercially and export oriented.

- Using NEPAD as a platform, set up an Africa-wide technical working committee on the Pharmaceutical sector to oversee the harmonization of the sector and establish a Mutual Recognition Arrangement for the registration of medicine, inspection of manufacturing facilities, funding of medical research and development, regulation, patent rights, etc.

- Certain parts of the value chain should be located in SADC member states where there is comparative advantage. That is, it might be necessary for SADC/African countries with a similar resource base collaborate in developing the value chain (or segments of the value chain). This approach has he advantage of allowing the transformation of African raw materials into finished goods within Africa, hence benefiting both the producers and consumers. Raw material producers benefit from the immediate market access for their produce; while consumers benefit from the relatively low prices for the finished products. Several other benefits (e.g. foreign exchange savings, employment creation, development and protection of indigenous plant species, preservation of indigenous intellectual property, etc) accrue to the SADC/African countries involved.

- The African market is potentially huge and holds a lot of promise for pharmaceutical products that provide immediate cures for common diseases like malaria, Aids, etc. This should be the main focus for development of the pharmaceutical products, medical equipments and instruments;

- Establish an aggressive capacity building programme, hosted by the identified Centres of Excellence, and supported by a special fund for innovation, skills development, and research and development in the Pharmaceutical Industry.

- For the production of export-oriented industries, African countries should agree to grant tariff exemptions to imported goods considered to be inputs for the local industry and which will be packaged, processed and re-exported. This would help contribute to the diversification of the manufactured exports within priority industrial sub-sectors. The reduction in tariff barriers would promote intra African and sub-regional investment and trade within the African continent.

- African countries should be proactive and take advantage of the fragmentation of the industrial production, which has a direct correlation with the diffusion of technology and transfer of know how.

- Incentives must also be provided at the policy level for which intermediary goods are structured in a manner so as to attract more medium to high technology content products in order to foster the upgrading process.

- Governments should act as facilitators of economic activities and empower the private sector to be the major operator in production and distribution. However, Government has to intervene in activities where there are market failures or where economic returns are negative.

- Accreditation of laboratories (including private sector laboratories) and provision of technological infrastructure will help to boost the long-term viability of the pharmaceuticals sector.

- Development of the Pharmaceutical Sector to carry out, inter alia, Clinical Research Outsourcing, production of Generics as well as addressing the Phytodrug sector.

- The Biomedical Industry is rapidly emerging as an engine of growth for the future. In that regard, there is need to identify and select a number of institutions/organisations which should be developed into regional centres of excellence for high-technology medical and biotechnological activities.

      - SADC-EU EPA Negotiating Principles and Objectives

In previous ACP-EU cooperation agreements, all ACP countries enjoyed non-reciprocal tariff preferences for their exports to the EU market. Under the Cotonou Agreement, this has changed in 2008, when reciprocal free trade arrangements (under so-called Economic Partnership Agreements (EPAs) negotiated at the regional level between the EC and the six ACP regions) should replace the previous preferential trade regime. The new agreements must be compatible with the rules of the WTO, development-oriented and build upon ACP regional integration initiatives. The new trade regime must also incorporate and improve upon the Lomé/Cotonou instruments regarding access to the EU market for the ACP countries.

The Cotonou Agreement and the ACP guidelines for EPA negotiations state the general objectives and principles the SADC members will adhere to in the EPA negotiations. Based on the Cotonou Agreement and the outcome of the first phase negotiations, both sides agree that the overall objectives of the SADC-EC EPA will be sustainable development of SADC countries, their smooth and gradual integration into the global economy, and to contribute to the eradication of poverty.

Trade liberalization is one of the intended means to achieve these goals, but given the structural frailties of the SADC economies, it is clear that trade liberalization in itself will not lead automatically to growth and sustainable development. Therefore, the EPA, together with other bi- and multilateral trade and development initiatives (as AGOA, “Everything But Arms”), is intended to tackle trade and development weaknesses in a more significant way than the Lomé conventions. By adopting a more holistic approach, the EPA can help SADC economies surmount their various supply-side constraints and build a more diverse and competitive production basis.

More specifically, the SADC-EC EPA will:

- promote sustained growth,

- contribute to enhancing the production and supply capacity of the SADC countries,

- foster the structural transformation of the SADC economies and their diversification, and

- support regional integration initiatives in the SADC region.

The new SADC-EU Economic Partnership Agreement (EPA) will contribute to SADC regional integration process particularly in enhancing the diversification, production and supply capacities of SADC countries in line with the objectives and goals of the SADC Regional Indicative Strategic Development Plan.

      - The major problems to be solved

Like most developing countries, agriculture is the cornerstone of the SADC countries economies. Unfortunately, agriculture alone is no longer able to provide reliable livelihood for the growing population in SADC.

The manufacturing sector and transformation of the local raw materials represent the greatest potential for employment and trade development in SADC countries. However, production of manufacturing goods and their commercialization on the regional and international markets suffer of the following key constraints:

- Poor product quality;

- Poor productivity, competitiveness and attractiveness of industrial sectors, especially those identified as priority;

- Limited market access due to barriers to trade (TBs and NTBs/SPS);

- Lack of international quality and service standards;

- Lack of reliable and mutually supportive relationships up and down the supply chain;

- Limited marketing due to problems with pricing, limited margins and inadequate promotions strategies;

- Inadequate/weak Human Capital development;

- Shortage of energy supply;

- High transaction costs resulting from high transportation and logistics costs;

- Weaknesses in provision of relevant information;

- Limited promotion of networking partnerships among African entrepreneurs within the region;

- Poor/lack of coordination in the regional infrastructure development;

- Restrictive regulatory environment;

- High cost of doing business.

  - Programme justification

      - The EPA Context

The prospects of the EPA’s entry into force reveal concerns and expectations, which seem contradictory and complementary at the same time:

- Certain fear that EPA turns only into a free trade agreement increasing difficulties for local companies;

- Anticipation that EPA will be a tool for the economic development and regional integration, which would provide the capacity building for national and sectoral institutions in order to improve the business environment able to promote the national value chains, regional integration and convergence.

As to the tariff disarmament, on the contrary, “the EU has clearly said that long transition periods, a phased introduction of tariff dismantling, exemptions from liberalization for sensitive products and a strong asymmetry between EU and ACP opening are perfectly acceptable and reasonable”.

“The EC market access offer to ACP countries in EPAs consists of duty-free, quota-free treatment for all imports. This treatment would apply from entry into force of the agreements for all products except for sugar and rice. For these two products, duty-free, quota-free treatment would be phased in over a transition period.

This offer includes the elimination of all tariffs and tariff rate quotas on products not fully liberalized under the Cotonou trade regime such as bananas, beef and other meat, dairy products, wheat and all other cereals, as well as all fruits and vegetables.

The EPAs are intended to be broad agreements, helping first of all to build regional markets and diversify economies in the ACP regions before opening up trade to build increased, balanced and sustainable trade between the two regions.”

In order to reach its effectiveness, the policy of liberalizing intraregional trade and interregional exchange with EU, needs to be supported by the permanent implementation of Upgrading Programme for the private companies, technical support institutions and their institutional environment so that the companies are able to better face an international competition at regional and international levels.

The development goals have an absolute priority in the EPA negotiating process and serve as the basis for the future relationship between EU and ACP grouping of countries. The new agreement performs thus as a response to the challenges of the world globalization and international development processes. In the spirit of the new partnership, the EPA negotiations and its implementation must be accompanied by appropriate policies implemented by ACP States, on the one hand, and by support measures provided by EU, on another hand. It is from this point of view that the latter committed it to help the Southern Africa region to improve its competitiveness, diversify its exports, create new jobs and to build its regional market. The objective is to develop fair partnership adapted to the specific conditions of the Southern African region that would go beyond such issues as market access and would take into account and focus on the constraints limiting production and exports through improving both quality and quantity.

      - Lessons learned

The general approach developed by the Programmes on Industrial Upgrading and Modernization takes into account the experience gained by UNIDO in implementing several thematic programmes in the context of trade liberalization with increasing emphasis of companies’ participation in international trade and their increased competitiveness. The lessons learnt from the experiments carried out by UNIDO in upgrading industries in UEMOA region as well as in other different countries (Tunisia, Morocco, Algeria, Jordan, Portugal and Senegal) were cumulated in the strategic approach and methodologies of formulation and implementation of the Programmes on Industrial Upgrading and Modernization. The major results of performance evaluation of UEMOA and EBAS quality programmes were also used.

The key principles of the lessons learnt are, in particular, as follows:

- To encourage strong political will to improve business environment by reducing administrative obstacles and eliminating barriers to trade;

- To promote the better participation of all parties interested in companies development in all phases of Programme’s implementation, including entrepreneurs themselves and professional associations. The evaluation of the projects intended to support the private sector has brightly demonstrated that the obstacles to which the businesses face are difficult to be revealed unless the entrepreneurs and trade associations identify them, assist in searching the possible ways of their solutions in close partnership with the public administration;

- To highlight the need in continuous and sustainable character of upgrading process;

- To stimulate visibility and effective involvement of the private sector and financial institutions with the aim to improve an access to credits;

- To promote effective and operational decision-making process based on good analyses of specific situation and national context leading to decentralize the Programme management process with putting the special emphasis on targeting national actors in every beneficiary country of the region;

- To ensure effective distribution of roles among regional, sub-regional and national institutions in management and implementation of the Programme with a clear definition of competences and areas of activity for each institution involved.

  - UNIDO Initiative

The present Programme has as an objective to support the efforts of SADC countries in reducing constraints and difficulties encountered by industries of the region as the result of trade liberalization. Nevertheless, liberalized markets are creating new opportunities to implement new industrial policy for enhancing the companies’ competitiveness and access to the new markets.

In parallel with other bilateral and multi-lateral programmes the UNIDO Initiative on Industrial Upgrading and Modernization could perform as one of effective tools in meeting challenges set-up by sub-regional and national competitiveness development initiatives. In particular, the Programme will aim to:

- Provide companies with technical assistance and financial support in implementing restructuring projects to improve their competitiveness and to better response to the new challenges of liberalized market;

- Reap significant benefits from trading opportunities created by trade liberalization through getting better access to both regional and international markets;

- Provide capacity building to specialized public agencies and industrial support institutions (technical centers and associations), whose weaknesses do partially explain the lack of performance in the most of SADC national industries;

- Enhance competitiveness of the greater part of the region’s industrial sectors;

- Promote diversification of the regional economy and encourage local processing of raw material;

- Improve business environment to make it favorable to the private sector (administrative procedures, access to credit, etc.).

UNIDO’s experience in implementing industrial upgrading programmes has demonstrated immediate effect on acceleration of industrial sector growth, and thereby contributing to the overall socio-economic growth and employment creation.

Held on 7-8 June 2007 in Gaborone, Botswana the Inaugural Meeting of SADC Industrial Development Forum (IDF) welcomed UNIDO’s initiative and approved the development of the proposed Industrial Upgrading and Modernization Programme.

# On 31st March – 2nd April 2008, in Johannesburg, South Africa, the SADC Secretariat held the Regional Validation Workshop which approved the draft programme. The SADC Secretariat, delegates from Member States, representatives of private sector and UNIDO took part in this workshop.

  - Main beneficiaries of the Programme

The main beneficiaries of the Programme are:

- Manufacturing companies, formal and informal SMEs and companies providing related services: The SMEs from each SADC member country eligible to the Programme will directly benefit from the UNIDO’s approach and methodology and will improve their productivity, quality management and export capacities, upgrade their equipment and enhance competitiveness.

- The regional and national institutions providing industrial support and professional education in SADC countries: These institutions will receive the technical assistance (in the form of institutional support and equipment) in formulating policies and procedures, implementing activities related to industrial upgrading, providing professional trainings and innovations, and improving competitiveness.

- The Ministries of Industry and Trade: They will directly benefit from the technical assistance provided within the Programme implementation. This will include capacity building programmes for the staff of ministries, national associations, private sector and consultants.

  - Articulation of the Programme between regional and national levels

The institutional nature of the Programme leads to the mobilization and involvement of all actors in the upgrading and modernization process into methodology based on:

- Indispensible complementarities between the regional and national institutions;

- The Programme presentation to the development partners as complementary to and coherent with the national programmes initiated and carried out in the Member States taking into consideration the national specificities of each country.

The SADC Secretariat will facilitate the following activities shared by all participating countries at the national level:

- development of information systems;

- development of the consultants database;

- conducting sectoral and other related studies;

- development and management of follow-up and evaluation mechanisms;

- supporting development of the national capacities.

At the national level, each Member State should select priority sectors for the pilot Industrial Upgrading and Modernization Programme development.  The ministries responsible for industry have to ensure establishment of appropriate mechanisms, giving them maximum autonomy and initiatives, allocating all necessary resources, associating the stakeholders, and setting-up the follow-up and evaluation mechanisms.

The National Steering Committees will be composed by representatives of the public, private and financial sectors. The National Offices for Upgrading and Modernization should be managed by experienced and autonomous experts.

Taking into account the sensitive and confidential character of information on companies’ upgrading and modernization, each file will be studied directly by the local committee.  It will act as the exclusive counterpart of the companies at national level.

The Programme should be flexible and adapted to the changing socio-economic and political environment. The following Diagram represents the repartition in Programme coordination between regional and national levels.

Diagram 2:

Programme Coordination at Regional and National Levels

  - Complementary activities to Upgrading Programme

The Industrial Upgrading and Modernization Programme is directly oriented towards companies and their immediate environment. Meanwhile, several other development institutions are acting in favour of competitiveness development and support to the productive sector in SADC countries. Those activities are developed at the regional and national levels and lead to improve business environment, infrastructure, human resources, competitiveness, investment and export potential, access to credit, microfinance, agro processing sector, institutional development, promotion of SMEs and craft industries.

In addition to the EU and its member states together with their specialized development agencies financing and implementing development programmes in the Southern Africa region, the other major donors and IFIs contributing to the socio-economic growth in the region at the macro-, sectoral and micro-levels include the World Bank, the European Investment Bank, the African Development Bank, UNDP, the United States and Canada through their international development agencies USAID and CIDA, respectively.

While the short-term, concretized, selective support programmes are less efficient, this Programme proposal offers a global approach, which will implement in its operational mechanism the complementarity strategy with the related activities of EDF, EU members and other financing institutions. It will aim at involving other financial partners to reach a multiplying effect of all programmes.

# The programmes complementary to the current initiative are numerous and largely spread among various sectors of manufacturing and services. The programmes are partially funded by national governments or regional institutions as SADC DFRC, with predominance of international and foreign donors such as EU, ESIPP, CDE, World Bank, USAID, IFC, MCA, FAO, UNDP, UNIDO, AfDF, GTZ, AFD.

  - Coordination of potential donors

# The Programme activities to be implemented jointly with International Cooperation Partners will be coordinated during the regular meetings initiated by the SADC Secretariat every three months.

- OBJECTIVES, COMPONENTS AND OUTPUTS OF THE PROGRAMME

  - Objectives

      - Global objective

The overall objective of the Industrial Upgrading and Modernization Programme is to contribute to the strengthening of industrial capacities of the SADC countries to face the double-challenge of regional and world integration and, in particular, in the context of economic and trade liberalization and diversification, to support efforts to reduce poverty.

      - Specific objectives

Specifically, the Programme aims to support the dynamics of upgrading and modernization of industries and related services, and to improve their competitiveness, growth and access to national, regional and international markets within the framework of trade liberalization and economic diversification, in particular, through improving productivity and quality, job creation and strengthening of technical support infrastructure.

Current Programme proposal covers:

Phase 1: 	The Programme will be piloted at the regional and national levels for a period of 3 years.  The Pilot Phase will consist of industrial upgrading and restructuring at the enterprise level and development of regional and national institutions supporting implementation and follow-up of the Programme.  This phase intends searching and developing the “success stories” through running some possible experiments.

Phase 2: 	The Roll-out Phase of the Programme will draw on lessons learnt during Phase 1 and will be opened to all the remaining priority sectors. The duration of this phase is 3 years with possible extension.

Each phase of the Programme will end with a comprehensive evaluation and review commissioned by the SADC Industrial Development Forum.

The outputs and respective activities could also be reviewed subject to the results of intermediate evaluations of the Programme implementation and/or according to the specific development priorities of the Member States.

  - Programme components and outputs

The Programme will be implemented through two integrated components:

- Support for upgrading and improving competitiveness of industries and related services;

- Establishment/upgrading of the technical support institutions.

The Programme is expected to be implemented through achieving the specific outputs described in the next section.

|  | Component I |
| --- | --- |
| Support for upgrading and improving competitiveness of industries |  |
| This component covers the key activities on upgrading and modernization of industrial companies in strict sense. The major beneficiaries are the companies of the priority industrial sectors largely contributing to national economies. They will benefit from activities on restructuring, upgrading and improving of their competitiveness. Together with the direct interactions with beneficiary companies, this component intends to target an institutional and legislative framework necessary for the success of the Programme. This component follows the various stages to be crossed within the Programme implementation. Several activities can be launched simultaneously as the component covers activities relating both to the pilot and roll-out phases of the Programme implementation. |  |
| Immediate Objective | Support the dynamics of industrial upgrading and improving competitiveness, overall economic growth and access to the national, regional and international markets. Development of the regional and national institutions for implementation and follow-up of the Programme on Industrial Upgrading and Modernization. |
| Problems to be solved | - To restructure and upgrade the industrial network to make it more competitive at the national and international levels; - Absence of policies, legal framework and mechanisms enabling funding of upgrading and modernization activities; - Lack of institutional capacities necessary to support upgrading and modernization activities. |
| Output I.1 | Strategic positioning study of 20 priority and contributing products/sectors (e.g.: agro-food, processing of metallic, non-metallic and chemical products, pharmaceuticals, leather and hides, cotton and textile, poultry farming, fisheries, etc.) taking into account national specificities and capacities determining industrial specialization. |
| Output I.2 | Thorough diagnosis and restructuring plans for beneficiary companies. |
| Output I.3 | Thorough diagnosis and upgrading plans for the companies eligible to the Programme (global approach and specific approach) |
| Output I.4 | Technical support and coaching of SMEs for the implementation of the upgrading activities in the beneficiary companies (priority to immaterial investments activities). |
| Output I.5 | Capacity building for the ministries in charge of industry, upgrading centres, SME, employer associations, banks, experts/consultants and trainers for the implementation and follow-up of the Programme. |

| Output I.6 | Formulate national Industrial Upgrading and Modernization Programme for each Member State. |
| --- | --- |
| Output I.7 | Design and provide assistance for the establishment of a legislative framework and procedures for the regional Industrial Upgrading and Modernization Programme at regional and national levels. |
| Output I.8 | Design and implementation of the regional and national programmes of communication and promotion of the Programme (development of promotional materials and thematic website for the SADC Secretariat and each country) and undertaking of “SADC Upgrading Tour” for the managers of industries at the regional and national levels and organization of information and dissemination seminars on Programme’s results for the different production. |
| Output I.9 | Promotion of projects on industrial partnership/industrial coaching among the companies eligible to the Programme. Providing support to negotiating process (business-plan and fund-raising)/strategic coaching. |
| Output I.10 | Feasibility study and establishment of financing schemes to facilitate access of local SMEs to funding necessary to implement upgrading and modernization activities and to fulfill their investment plans. |
| Output I.11 | Setting-up of a Monitoring Framework for Industrial Upgrading and Modernization Programme at national and regional levels. |
| Output I.12 | Strengthening of capacity of enterprises, associations and related services in the informal sector (entrepreneurship, bookkeeping, financing, management, marketing, production management, etc.). |

| Component II |  |  |
| --- | --- | --- |
| Establishment/upgrading of the technical support institutions |  |  |
| This component is a matter of activities complementary to upgrading actions, dealing basically with environment of the Programme, notably, through providing activities related to strengthening capacities of the technical support institutions and those of quality promotion. |  |  |
| Immediate Objective | Upgrading and modernizing industrial support institutions Improving quality of business-climate and exports capacity. |  |
| Problems to be solved | - Weak capacities of institutions for technical assistance in upgrading and exports promotion; - Deficiency in institutions providing technical and professional education and training; - Narrow range of business support services; - Limited support for promoting company competitiveness; - Non-conducive business and macro environment. |  |
| Output II.1 | Thorough diagnostics, formulation and implementation of the upgrading plans for technical centres promoting priority and key export sectors (sectoral technical centres, research institutions, export promotion agencies, test and analysis laboratories, specialized institutions for vocational training, national technical expertise, networks and information systems). |  |
| Output II.2 | Launch of the HACCP and certification ISO 22000 for selected companies. |  |
| Output II.3 | Assist with the implementation of programmes of traceability for specific and priority products having high potential for export (meats, fish, fruits and vegetables, flowers, cashew nut, coffee, cocoa…). |  |
| Output II.4 | Implementation of Quality Management Systems and certification of ISO 9001 QMS at beneficiary companies. |  |
| Output II.5 | Networking of intermediary organizations from SADC region and EU and strengthening professional organizations. |  |
| Output II.6 | Promotion, creation and assistance for the establishment of export consortia. Formulation of support measures and a favourable legal framework for the export consortia (at regional and national levels). |  |
| Output II.7 | Strengthening capacities of investment promotion agencies and establishment of an investment platform in order to respond to the needs of investors and operators in the area of upgrading and modernization. |  |
| Output II.8 | Establishment of Subcontracting Exchanges and “aftercare” services. |  |
| Output II.9 | Support to and industrial coaching of investments for developing new products in Southern Africa and promoting industrial diversification. |  |
| Output II.10 | Strengthening and upgrading of the technical and professional training institutions. |  |

Annex III of the document provides the detailed list of activities leading to the achievement of the above outputs, whereas Annex IV presents their implementation schedule.

- APPROACH AND CRITERIA OF ELIGIBILITY TO THE PROGRAMME

The Industrial Upgrading and Modernization Programme developed for SADC countries is mainly based on the various experiences of enterprises upgrading implemented in several countries notably Tunisia, Algeria, Senegal, and currently underway in UEMOA countries.  It also takes into account the recommendations of evaluations made by the EU and UNIDO particularly for upgrading projects in Tunisia, Algeria and Senegal.

These approaches aim to upgrade and improve competitiveness of companies with potential to further development through strengthening productive capacities, on one hand, and improving quality of related services and business environment in general on another. This will allow companies to build capacities necessary to produce manufacturing goods in compliance with different international technical regulations and quality standards.

The approach also calls for undertaking actions that intend to improve the financial situation of companies, their productive performance and energy efficiency, ability to produce according to international standards and technical requirements and to facilitate their integration into the world market. The figure below gives an overview of UNIDO’s Upgrading Approach.

Diagram 3:

Process of industrial upgrading and modernization

  - UNIDO Approach

UNIDO’s approach leads not only to providing direct assistance to the companies but also to strengthening of institutional environment and technical support institutions, consolidation of economic data and its dissemination, and to development of specific and tailored programmes. The approach is based on the following components:

      - Upgrading and Restructuring

This approach has four consequent steps: the pre-diagnostics, the strategic diagnostics, the formulation and implementation of the plan for restructuring and upgrading.

- The pre-diagnostics consist in conducting research campaign based on questionnaires, which are administered (1) to determine the eligibility of the enterprises to the plan for restructuring and upgrading, and (2) to identify the field of survey to formulate and adopt the diagnostics and plan for restructuring and upgrading. The declaration of interest will be a part of the questionnaire to serve as an attribute of enterprise’s fully voluntary participation in the current Programme.

This step of the process determines whether the company needs to go through a prior stage of restructuring to benefit ultimately from the upgrading stage.

- In the context of globalization and rapid technological progress, the strategic diagnostics aim to analyze competitiveness of the local companies. The special emphasis will be put on launching the Free Trade Zone within SADC in August 2008 and application of the Common External Tariff (CET) by 2010.

The diagnostics will thus reveal the strengths and weaknesses of the companies and will allow identifying the strategies to be followed as well as the short and medium-term actions for upgrading and modernization to be implemented within this Programme. The diagnostics will also propose a financial plan to carry out the selected actions.

- The restructuring plan covers mainly the structural and financial adjustments which could lead only to conversion or liquidation of nonviable activities or to financial reorganization of the enterprise. The objective of restructuring plan is to enable companies to become financially sustainable and to meet the eligibility criteria to benefit from the upgrading plan.

Once the enterprise implements its restructuring plan, it is eligible to subscribe to the upgrading plan. In this case, it will first update the initial diagnostics followed by elaboration of upgrading plan.

- The upgrading plan will mainly cover or review:

- The short- and medium-term strategy and objectives;

- Already implemented activities to raise the companies’ interest;

- The action plan of immaterial investments activities with special accent on companies’ competitiveness;

- The plan of financial sustainability of the company.

There are two types of upgrading activities:

Material upgrading activities in the form of acquisition and installation of the upgrading, laboratory and production equipment;

Immaterial upgrading activities: which may include training of companies’ staff, direct assistance of experts in the establishment or development of the production, sales and quality management systems, support in ISO 9001, 14000, 17025, 22000 certification, introduction of HACCP system, purchase of software, establishing accounting system, audit on energy management, energy saving activities, etc.

The UNIDO approach considers also assistance in the implementation of upgrading action plans according to:

The global approach of companies upgrading, which includes global strategic diagnostics, formulation of upgrading plans and technical assistance in implementing priority activities; and

The specific approach, which consists in assessment of company’s specific problem and assistance in implementation of related activities.

      - Upgrading technical support institutions

Upgrading technical support institutions is a key prerequisite to improve marketing and productive capacities and competitiveness of industries.

The majority of companies in SADC region suffer from considerable technology gaps mainly characterized by a lack of know-how on technical procedures and quality/safety management systems along with the absence of innovation initiatives in introducing new products and technologies. Moreover, ineffective exploitation of productive capacities and inadequacies in equipment maintenance lead to fabrication of defective goods or to the total suspension of production process.

Often overwhelmed by these technical and organizational shortages, the companies are limited in their capacities to optimize their technological process that determine their competitiveness and their place in the market. As a result, these companies are unable to produce goods that can respond to the current market needs and meet international quality standards, sanitary and safety requirements.

One of the main reasons for this appears in the weak technical skills and qualification of the technical support institutions. Their technical capacities are insufficient to satisfy the real needs of the industrial sector.

The current situational analysis shows that the national R&D and training institutions, the specialized technical centers and laboratories, the controlling, auditing and certification bodies do not possess the necessary capacities to support the companies, which, in consequence, have to seek the foreign expertise that brings to the companies additional costs and thus affects their competitiveness.

It is, therefore, crucial to address capacities of technical support institutions within the implementation of the Upgrading and Modernization Programme. The proposed approach, in particular, recommends:

Step1: To assess current situation in the area of the technical support to industrial sector and priority related services. This step should indentify (i) the number and list of technical support structures to be strengthened within technological upgrading activities and (ii) the nature and extent of needs in technological upgrading.

Step 2: To prepare the plans for technological upgrading for each of the beneficiary structures. These plans, prepared in close cooperation with the national counterparts and Programme beneficiaries, will particularly include the first-priority immaterial and material investments activities as well as the action plans.

Step 3: To implement technological upgrading plans through:

- Upgrading infrastructure and equipment to attain compliancy with international standards and technical requirements;

- Upgrading methodologies for operations and technological process;

- Organization of trainings in horizontal and sectoral competencies (technology, quality, safety, standards/certification, etc.);

- Direct assistance and training throughout the exploitation process.

The following results are expected:

- Technical centres and training institutions strengthened or established in various industrial branches;

- Critical mass of national and/or regional expertise trained and operational;

- Regional network of institutions for technological support established and operational.

The technical support institutions will also play the role of centers for Business Development Services (BDS) providing institutional and technical support for strengthening the business-support infrastructure as well as directly for the establishment and operations of small and medium enterprises in the manufacturing sectors.

The technical support or training institutions will be established for sectors which provide a critical mass of enterprises sufficient for financial sustainability of such institutions. For the sectors/countries with a lower number of enterprises the Programme will establish the BDS Centres to respond to the needs of local SMEs operating in various manufacturing sectors.

Annex VI gives examples of the sectoral support institutions.

      - Strengthening economic information infrastructure (Strategic positioning studies)

An access to the economic data and information has always served as an essential element in decision-making process both for political and business leaders helping them to build their development strategies at regional and national levels.

However, such economic information in several SADC countries is often vast, non-systematized or sometimes even missing, especially when it refers to the sectors defined as of priority or contributing the most to the national economy or playing the key role in country’s socio-economic development.

In order to address this information gap, it was decided to conduct the survey on identification and strategic positioning of around 20 priority and contributing sub-sectors/products taking into consideration the regional and sub-regional contexts to match the countries’ specific product line (i.e. food processing, cotton and textiles, minerals processing, pharmaceuticals, etc.).

The results of this survey reflect the basic features of industrial sectors or their branches by each country or throughout the region. They track an evolution of the key economic indicators over the last several years and reveal the investment opportunities in emerging sectors. Besides, the survey enables analysis of intra- and interregional competitiveness of the local companies and proposes the actions to improve their position.

      - Development of consortia and export promotion infrastructure

Several countries that already implemented the programmes on upgrading have an experience in establishing consortia in order to strengthen export capacities of the national small and medium size companies.

The consortia give the best fit to SMEs that have already reached an appropriate production level and, possibly, have some experience in exports, but still need assistance to face the challenges of globalization and trade liberalization processes.  These conditions are usually met by manufacturing or services companies. On the other hand, small agricultural producers or crafts workmen do not possess the necessary production capacities, human and financial resources to face the demand and competition of the world market. The export consortia can also be established for cooperatives that meet the criteria set up for the SMEs.

The benefits of establishing and joining the exports consortia or exports promotion network comprise:

- diversification in goods supply;

- better negotiating capacities while bargaining with potential buyers;

- prospects to expand the exports destinations to remote regions;

- better understanding of markets and reduction of business risks;

- reducing the costs of promotional activities (common website/production catalogue, exhibition booth, etc.) and less risks related to exploring and exporting the new business opportunities abroad.

Current approach offers the following 4 steps of establishing exports consortia and export promotion networks:

- Identification of national partners in public and/or private sectors (export promotion agencies, sectoral associations, chambers of commerce and industry…);

- Training of export consortia’ leaders to support in their creation and ensure their sustainability;

- Awareness raising activities and identification of target groups: to organize in cooperation with national partners the seminars and meetings which will present the concept, services and benefits of export consortia;

- Distribution of questionnaires to companies participating in the seminars inquiring about the interest expressed;

- Selection of the companies interested in creating an export consortium. The selection process will gather together a group of companies coherent in terms of activities/production, size, organizational structure and human resources, knowledge of export techniques, their current and targeted markets, required services, etc.;

- Assistance to selected companies in establishing and launching the export consortia and export promotion networks notably in fixing their:

- common objectives;

- services offered;

- organization (human resources, logistics, etc.);

- the most appropriate juridical status;

- mechanisms of self-financing (membership fees, possibility of external funding, etc.);

- business plan, promotion programme and budget;

- assistance needed to carry out the business plan and promotional activities.

- Assistance to the national partners in establishing the legal and financial assistance measures.

The awareness raising activities as well as the launch of 2 to 3 pilot exports consortia are envisaged within the Phase 1 of the Programme implementation.

      - Promotion of partnership and industrial coaching

Investment and technology promotion is one of the most efficient ways to ensure companies’ development, acquire advanced experience and capacities and to gain access to new markets.

This is especially pertinent to the SMEs in SADC countries where imperfections in business environment largely affect the companies’ growth. The bottlenecks for the business development, in particular, include:

- an absence of technical and markets monitoring;

- difficulties to access the technical or normative information;

- lack of well-qualified staff;

- lack of specific skills, notably in the field of quality or safety procedures;

- difficulties in accessing financial resources.

The partnership with similar companies or being a part of the global supply chain can be used as a “strategic arms” promising the quick solutions to the above problems. The more the companies are homogeneous, the more relations are facilitated among them and the stronger is partnership.

Despite the existence of historical background in business ties between the companies of SADC countries and European Union, there is still a big gap between them in the terms of performance and overall development.  Moreover, notwithstanding the regular character of those ties they are often few, short-lived and unfavorable to African companies.

After initial assessment of existing companies, the original methodology of technological and managerial upgrading will promote the volunteer partnership among the participating companies. This methodology pursues favoring development of interregional cooperation through experience exchange between entrepreneurs of EU and SADC countries, conducting industrial coaching missions, etc. It is also intended to establish a network of support institutions for private sector development in order to ensure sustainable contribution to the partnership promotion.

These activities could be carried out through and by UNIDO’s Investment and Technology Promotion Offices (ITPO), the Centers for the Development of Enterprise (CDEs) and the support institutions and investment promotion agencies of SADC countries.

Notably, these activities will comprise:

- Identification of market opportunities and technological scenarios and analysis of existing companies’ capacities for partnership;

- Development of partnership and investment strategies and formulation of related projects and putting them on the platform;

- Training of business executives on negotiation skills and formulation of partnership contracts and development of promotional materials necessary for communication of partnership policies;

- Organisation of promotional and mobilization seminars abroad and identification of potential partners;

- Support in searching for financial partners;

- Supporting enterprises in effective accomplishment of their partnership agreements/contracts.

      - Establishment of traceability system

Traceability is a preventive system that deals with quality and safety management of foodstuffs production. Once the food quality/security alarm system alerts, a good traceability system facilitates the callback of risky production and helps to localize the point-of-origin of the problem.

The capacities to undertake the trace-back and trace-forward activities at every stage of the food production and distribution chain are crucial to boost the customer confidence in alimentary products especially in developed countries.

Agro-alimentary traceability consists in tracking of and demonstrating the good agro-alimentary practices including collection, documentation, maintenance and use of information related to the entire process of food supply chain - from provision and production of food-staffs to their sales. This system will not only provide the safety and quality guarantees to the customers or business partners, it will also inform the users on the history, origin and life duration of manufactured goods. It also facilitates the management procedures during crisis situations related to the breach of the safety or quality rules.

This activity thus includes:

- Identification of the sensitive and priority agro-food production/sectors and analysis of production/distribution chains for selected products;

- Organization of information seminars on traceability and access to European market;

- Development of a traceability manual (according to ISO 22005 Standard) and training of trainers;

- Implementation of a (manual/automatic) traceability system in the selected pilot companies;

- Empiric verification of effectiveness and performance of traceability systems (farm-to-fork);

- Adaptation of the procedures for the implementation of traceability systems.

If the companies of SADC agro-food supply chain wish to export their production to EU and international markets, the introduction and establishment of such systems appear therefore indispensable and critical.

To accomplish this task, the several pilot companies of agro-sector will serve as the models for establishing such systems and development of integrated programme covering the largest part of the agro-alimentary sector in all SADC countries.

      - Supporting the informal sector SMEs

The industrial sector in SADC countries is dominated by the small and medium size enterprises operating mostly in informal sector, which is a product of rational behavior of entrepreneurs that desire to escape state regulations. Information on these companies is thus rare and nearly absent although the sector represents a great interest as a base for the socio-economic development of the region.

In order to overcome the constraints of this sector and to take advantage of its opportunities, the Upgrading and Modernization Programme intends to assist the companies of informal sector as well as to undertake various activities (awareness raising, technical assistance and development programmes) to involve and integrate the local companies into the formal economic environment.

These actions will include, most notably:

- Undertaking studies of the informal sector in each SADC country where such a study has not been carried out in the last five years;

- Awareness raising among informal sector companies on the benefits of joining the formal sector (access to financing, security, visibility, etc.);

- Industrial coaching for groups of craftsmen (joinery, weaving, garment, dye-works, small production of furniture, jewellery, etc.);

- Modernizing the methodologies of the products design to ensure conformity with the modern hygiene and safety standards;

- Improving conditioning and packaging of production to facilitate its preservation and sales;

- Providing premises for companies and purchase of small equipment;

- Technical assistance in searching and acquisition of modern equipment more adapted to the local conditions and of better performance;

- Assistance in the field of manufacturing methods and in development of the new products;

- Providing basic accounting and technical trainings;

- Assistance on formulation of the requests for funding;

- Assistance in establishing the labour unions and/or associations of suppliers and retailers to facilitate access to funding and to improve availability of the raw materials.

  - Criteria of eligibility to the Programme

The criteria of the companies’ eligibility to the Programme will be finalized and validated by the National Steering Committees, which will take into account the specificities and the size of industrial sector in each of beneficiary states.

In general terms, eligibility to the Programme is open to any interested and voluntary small and medium-sized enterprise if:

- it was created according to respective national legislation (including industrial enterprises that may have part of their production systems in non-SADC countries);

- it belongs to manufacturing sector or it provides services related to industrial activities.

The proper definition of SMEs varies from country to country, depending on the purpose for which the definition is used, the overall level of economic development (a large enterprise in Malawi may be considered a small one in South Africa) and using different criteria like employment or capital invested. Generally however, in most developing economies the following broad categories would appear to apply within this Programme:

- Micro enterprises: employment level below 10;

- Small enterprises: employment level from 10 to 49;

- Medium enterprises: employment level from 50 to 249.

Additional programme eligibility criteria are listed below.

      - Upgrading the formal sector SMEs

- 2 years of productive activity is a requirement;

- Employing (over the year under review) a total staff complement of:

- 10 or more for the enterprises in manufacturing; and

- 5 or more for the firms supplying services to industries;

- Meet the following financial performance criteria for the year under review named hereafter year n-1:

- A positive net worth for the year under review or year n-1,

- A positive turnover for the last financial year.

In the countries of less than 100 enterprises, the criteria of minimum staff level will be decreased.

The Programme allows conducting simultaneously both the global and specific upgrading plans. The company, according to its performance level and priorities, will be able to choose the best possible solutions proceeding through a short and free-of-charge pre-diagnostics.

Implementation of the global upgrading plan will improve company’s entire performance dealing with its management and production systems, whereas the specific upgrading plan will only touch the particular functions through the specific activities.

Skipping the long diagnosis or the business-plan elaboration, the specific approach will allow the rapid introduction of the state-of-the-art management systems (CAM, CAMM, ERP, ITC), marketing techniques, cost calculation tools, quality management methodologies and techniques, etc.

      - Financial restructuring

The SMEs not meeting the financial performance criteria to be eligible to the Upgrading Programme will be able to benefit from the Restructuring Programme. The latter will assess the technical, financial and managerial capacities of the company in order to identify the actions necessary to enable the company to carry out financially sustainable and profitable business. Such company will be a subject of financial aid provided within the plans of material and immaterial investments necessary to restart company’s activity.

Thus, a company eligible to the Restructuring Programme has unbalanced financial structure but still possesses the strong development and export potential.

To benefit from the Restructuring Programme, a company should not have the insolvency status or be bankrupt.

      - Assistance to informal sector SMEs

The Small and Medium Enterprises (SMEs) of the informal sector can benefit from specially tailored upgrading activities.

The eligibility criteria to participate in these activities are:

- the real productive activity with its physical acknowledgment;

- new jobs creation or existence of at least 4-5 permanent or associated positions;

- acceptance of transparency conditions and openness towards national and international economic environment.

Targeted sectors

The Programme will target the informal sector companies that constitute the nascent value chains based on local resources and raw materials. Such sectors include, but are not limited to the following activities:

- Fisheries and seafood processing;

- Transformation of the local raw materials (e.g. palm or peanut oil production, wine-making, beverages production and brewery, distillery, traditional soaps and other agro-industrial goods production);

- Transformation and processing of mineral resources, production of the basic mineral and construction materials (salt, cement, bricks, granite, etc.);

- Industrial and traditional production of textiles and garments, leather and leather goods;

- Industrial services, small-size metal processing, mechanic machinery, electric and electronic equipment, small foundries and motors service centres;

- Forestry, wood production and industrial derivatives;

- Printing and communication services.

Content of the Programme

As its objective the Programme will have:

- Immaterial investments activities

- direct assistance to “entrepreneurs” of the informal sector through tailored training programmes and/or direct technical assistance;

- indirect assistance by creation of Specialized Micro Centres for Support (joinery, oil production, canned foodstuffs, textile and garments, leather, etc.) or the Growth Centres, business incubators, etc. where the trainers together with the local experts (trained within the Programme) will provide sustainable assistance.

- Material investments activities

The financial allowance for equipment modernization could be either:

- individual, for small manufacturing and support equipment such as woodworkers, furnaces, presses, packing and parcelling equipment, dehydrators and pasteurizers, smokehouses, small tool-shops, etc.;

- or for a group of craftsmen (on multi-function platform) to provide them with common equipment such as generators, cool-houses and storage rooms.

      - Examples of eligibility criteria applied in previous upgrading programmes

This section gives examples of eligibility criteria to upgrading programmes previously implemented in other African Countries.

Programme on EPA Support, Cameroon

- Be a private sector company of 2 years minimum in productive activity;

- Financial solvency;

- The company should not be a subsidiary of a multinational corporation;

- Operations in one of the identified priority sectors;

- Positive turnover of FCFA 200 millions-10 billion;

- Possess technical and organizational capacities to carry out upgrading activities;

- Be able to provide certified financial statements;

- Voluntary participation in the programme;

- Commit to respect the key principles of upgrading programme.

UEMOA Regional Upgrading Programme

- Industrial companies established in UEMOA Member States and operating for at least two years;

- High potential in productive performance and financial solvency;

- Strong commitments to modernize and innovate;

- Companies considered performing in sustainable manner even within liberalized international trade environment.

National Upgrading Programme, Tunisia

- Industrial enterprises and service providers with strong growth potential;

- Companies operating for, at least, two years;

- Companies experiencing financial difficulties are not eligible.

National Upgrading Programme, Senegal:

- Voluntary participation;

- Be a private entity established under national legislation and financially transparent;

- Be in operations for the last two years;

- Annual turnover below FCFA 15 billion;

- Be operational and solvent (neither under liquidation nor prosecution);

- Be able to mobilize internal or external funds to finance upgrading programme;

- Do not belong to financial sector, trade and realty activities or other services;

- Be able to provide financial statements certified by external audit;

- Commit to respect the key principles of upgrading programme.

- FUNDING AND BUDGET OF THE PROGRAMME

  - Funding of the Programme

      - Upgrading activities

The Programme aims to upgrade a certain number of companies selected from priority sectors, which have strong potential for the high value-added and large export and employment opportunities. These criteria will be completed by information on production of these companies sensitive to the progressive tariff elimination. Such information will serve for assisting the companies to improve their productivity and quality in order to withstand competition from imports.

The following services will be provided by the experts within the technical assistance activities of this Programme:

- Conducting pre-diagnostics to assess eligibility of the company and to choose between specific and global strategic diagnostics to be carried out at the company;

- Global strategic diagnostics, which shall include the analysis of the different upgrading options and formulation of the business plan resulting from the strategic option selected and validated by the entrepreneur;

- Technical assistance and coaching specific to each company as a part of plan for immaterial investments activities;

- Assistance during the procurement stage of material investments plan (preparing invoices and specifications, choosing providers/subcontractors).

The range of services that compose immaterial investments plan is very broad (see Annex V) and notably includes activities aimed at:

- Strengthening of management systems (management, production, maintenance, marketing);

- Identifying the needs in management/administration software;

- Identifying the needs in human resources and training activities;

- Improving performance of the information and quality management systems;

- Ensuring availability of the relevant information in order to facilitate access to international market;

- Assisting companies in implementation of ISO 9001 and ISO 22000 management systems, introduction of energy-saving systems, partnership development, etc.;

- Assisting in elaboration of specifications and terms of references for the activities delegated to third parties;

- Ensuring validation by the company’s top management of immaterial and material investment plans prior to proceeding to the upgrading plan.

The material investments plan entails purchasing and installation of equipment that will facilitate removing the bottle-necks and modernizing the technological processes identified in the Business Plan.

The experience of industrial upgrading and modernization programmes implemented in other countries (Tunisia, Senegal, Algeria) shows that “immaterial investments” component represents 12-20% of the total costs of company’s upgrading. When the company decides to opt for the specific upgrading plan, this share increases to 100%.

The process of company upgrading is, first of all, a qualitative development that aims to enhance the competitiveness of companies through the totality of processes and actions leading to improving the quality of goods, reducing the costs (of raw materials, energy and labor), cutting down waste generation, improving productivity, shortening the production cycles and organizing the maintenance and manufacturing processes. As a result, and since these actions do not necessarily require increasing installed capacities, UNIDO recommends an indicative system that favors immaterial rather than material investments.

Thus, the direct aid or financial incentives, as well as technical assistance to be provided by this Programme, promote immaterial investments activities. The beneficiary companies should also benefit from the parallel investment promotion programmes that are currently under implementation or in the pipe-line in each participating country.

      - Funding of upgrading activities

The proposed financial incentives are intended to attract, stimulate and guide companies wishing to participate in the Industrial Upgrading Programme. These financial incentives slightly differ from one country to another. The table below presents the allowance ratios applied in three different countries.

Table 14:

Financial Aid Ratios for Upgrading Activities

| Activities | Tunisia % aid/aid ceiling | Senegal* % aid/aid ceiling | Algeria % aid/aid ceiling |
| --- | --- | --- | --- |
| Immaterial investments: |  |  |  |
| - Financial aid for diagnostics leading to formulation of upgrading plan | 70% € 17 500 | 80% € 20 000 | 80% € 18 000 |
| - Financial aid for other immaterial investments activities of upgrading plan | 70% € 41 000 | 70% | 80% No ceiling |
| Material investments: |  |  |  |
| - Financial aid for self-funded material actions | 20% No ceiling | 20% € 123 000 | 10% € 200 000 |
| - Financial aid for externally funded material actions | 10% No ceiling | 30% € 123 000 | 10% € 200 000 |
| Total Financial Aid | No ceiling | € 300 000 | No ceiling |

It is significant to note that these financial grants are assigned only after the execution of all obligations contracted between the company and the Upgrading Office. Nevertheless, in the case of Algeria, to encourage companies to make immaterial investments, the cash advance of 30% of the financial aid was granted whereupon the signature of the contract between the company and Upgrading Office.

The table below gives an overview of the average costs of the upgrading process.

Table 15:

Average costs of upgrading actions

| Activities | Tunisia |  | Algeria (2004) |  | Senegal* |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Amount (Euro) | % | Amount (Euro) | % | Amount (Euro) | % |
| Cost of immaterial investments activities | 115 000 | 13% | 232 000 | 14% | 60,000 | 15% |
| Cost of material investments activities | 765 000 | 87% | 1 400 000 | 86% | 240,000 | 85% |
| Total costs of upgrading actions | 880 000 | 100% | 1 632 000 | 100% | 300,000 | 100% |
| Average amount of financial aid | 127,000 | 14% | 325,600 | 20% | 123,000 | 16% |
| Number of companies | 2 262 |  | 64 |  |  |  |

*	The average cost of overall upgrading process per company admitted by authorities, AFD and UNIDO is €400000.  For UEMOA Programme, the accepted average upgrading cost is €400000. In Egypt, the total amount of financial aid provided is €100000 per company.

      - Average budget of the immaterial investments activities

In order to estimate the cost of immaterial investments plan we assume there are two groups of beneficiary enterprises employing (a) 10 to 19 and (b) 20 to 99 employees according to the following table.

The standard indicative budget for Upgrading Programme will be spread out over the period of 6 to 18 months for formulation of the Global Strategic Diagnostics and industrial coaching of companies on implementing Upgrading Plans. This standard budget presented below takes into account:

- Provision of the technical assistance of 45 and 150 man/day, respectively to the two groups of companies, with an average of €350 per day for one national/international expert. It must be noted that 45 m/d for the companies group of less than 20 employees can include the training activity for the team of trainers to diffuse the certain knowledge (food conservation, textile, garment, etc.).

- Provision and implementation of immaterial investments activities by national and international institutions and experts.

Table 16:

Estimation of man-days and costs related to immaterial investments activities

|  | 10-19 employees |  | 20-99 employees |  |
| --- | --- | --- | --- | --- |
| Immaterial investments activities | # man-day | Average cost (Euro) | # man-day | Average cost (Euro) |
| 1. Diagnostic study and formulation of upgrading plan | 10 | 3 500 | 20 | 7 000 |
| 2. Coaching | 5 | 1 750 | 10 | 3 500 |
| 3. Assistance in Marketing (market analysis, sales plan, training) | 5 | 1 750 | 10 | 3 500 |
| 4. Conception and setting-up of the bookkeeping and the cost price calculation systems | 5 | 1 750 | 10 | 3 500 |
| 5. Industrial coaching on management of production process | 10 | 3 500 | 10 | 3 500 |
| 6. Partnership |  |  | 10 | 7 000 |
| 7. Establishment of traceability system |  |  | 20 | 7 000 |
| 8. ISO 9001, ISO 22001 development (including certification costs) |  |  | 30 | 10 500 |
| 9. Conformity with HACCP (including certification costs) | 10 | 3 500 | 30 | 10 500 |
| 10. Operational website |  | 4 000 |  | 3 000 |
| 11. General and analytical accounting software |  | 5 000 |  | 5 500 |
| 12. Sales management software |  | 5 000 |  | 5 000 |
| 13. Inventory accounting software |  | 5 000 |  | 5 000 |
| 14. Computer Aided Maintenance Management (CAMM) |  |  |  | 8 000 |
| Total | 45 | 34 750 | 150 | 82 500 |
| Costs covered by company: 20% |  | 6 950 |  | 16 500 |
| Costs covered by the Programme: 80% |  | 27 800 |  | 66 000 |

Thus the average cost of the technical assistance under the immaterial investments activities would be approximately €46.000.

Table 17:

Estimation of the average cost of immaterial investments activities

|  | Percentage of companies | Immaterial investments activities | Average cost of TA to be covered by Programme | Calculation of the av.cost of immaterial TA |
| --- | --- | --- | --- | --- |
|  | (1) | (2) | (3)=(4)*80% | (4)=(3)*(1) |
| 10-20 employees | 60% | €34 750 | €27 800 | €16 680 |
| 21-100 employees | 31% | €82 500 | €66 000 | €20 460 |
| 100 employees and more | 9% | €123 750 | €99 000 | €8 910 |
| Total | 100% |  |  | €46 050 |

      - Budget for group actions

Some of immaterial investments activities necessary for upgrading plan are tailored for the group of companies or entire industrial branches on the basis of following estimations:

| Average annual budget for development, management and follow-up of export consortium of 10 companies (case of Tunisia and Morocco) | €70 000 |
| --- | --- |
| Average budget for sectoral studies and strategic positioning of priority and specific branches, products and sectors (case of Tunisia and Morocco) | €50 000 |
| Budget for establishment of subcontracting exchanges (3-year investments and operational costs) | €150 000 |

      - Investment and operations budget estimates for Upgrading Offices:                   Case of Senegal

| Staff: | 5 employees (director, 2 engineers, specialist on communication and training, and 1 financial specialist), 1 administrative assistant, 2 drivers, 1 courier and 1 cleaning lady. |
| --- | --- |
| Annual operational budget: | €150 000 |
| 3-year budget of investment: | €65 000 (6 PC work-stations with inverters, printer, multi-media unit, communications facilities, office, 2 vehicles, air-conditioners…). |

      - Proposed funding scheme

The diagnosis and action plans for both upgrading and modernization will be financed at 80% of the total budget amount. The following table describes proposed funding scheme:

Table 18:

Scheme of funding Programme activities

|  | Restructuring | Upgrading |
| --- | --- | --- |
| Diagnostics | 80% | 80% |
| Investments - immaterial - material | 80% 20% | 80% 20% |

  - Budget of Upgrading and Modernization Programme

Estimation of the budget will take into account the experience of UNIDO in implementing similar programmes in other developing countries, in particular, in Tunisia, Senegal and UEMOA region, as well as the results of country visits to SADC Member States.

At present, it is very difficult to determine the exact number of companies to be modernized, the scope of the technical support institutions to be established or strengthened and the limits of budget to be assigned to the Programme. Therefore the calculation of the budget will be based on the nature of expenditures, covering both variable and fixed costs, and, as result, 3 budget scenarios will be proposed.

Based on UNIDO’s experience, absorption capacities in SADC countries, calendar of liberalization, and demography and the size of beneficiary companies, the overall budget of the Programme was split by respective phase as follows:

- 20% for the Pilot Phase (overall and specific upgrading of the formal sector companies);

- 80% for the Roll-out Phase (overall and specific upgrading of the formal sector companies).

### Number of companies potentially benefiting from the Programme

The present Programme proposes three hypotheses (high, middle and low) which fix corresponding numbers of beneficiary companies to be covered by the Programme. The three respective budget scenarios have as an objective to target 12%-33% of SMEs currently operating in the region.

The low, medium and high hypotheses were formulated with strong and equal reference to the following factors:

      - Willingness and readiness to provide appropriate management and promotion of the Programme;

      - Terms of eligibility to the Programme (possible verification of the companies’ performance from financial results); and

      - Conditions of the companies' access to funding.

Intermediate evaluation of the above factors during the Pilot Phase will help improve the overall orientation and efficiency of the Programme.

As “nothing is more successful than success”, experience of upgrading programmes in Tunisia, Senegal and Algeria, showed that success of the first activities implemented at beneficiary companies has been a determinant for the entire programme performance ensuring the better participation of the private and public capital in financing the programme activities.

Finally, assuming that the "low" hypothesis underestimates companies’ involvement, the Programme will be always able to adjust the eligibility criteria to the new conditions and available resources.

These hypotheses also assume involvement of all concerned actors. The rhythm of the Programme’s start-up will largely depend on the national capacities to set up the proper programme implementation mechanisms and the quality of activities ensuring better cooperation and access to financing.

Thus, the three hypotheses set up the following number of beneficiary companies to be addressed by the Programme:

“Low” hypothesis: 		1425 formal sector companies

“Middle” hypothesis: 		2130 formal sector companies

“High” hypothesis: 		2850 formal sector companies.

The same hypotheses will be applied for the informal sector companies.

Based on the above, the beneficiary companies would be collated between the different intervention plans along the following lines:

Table 19:

Distribution of companies/support centers according to nature of intervention for 3 hypotheses

|  | ## “Low” hypothesis | ## “Middle” hypothesis | ## “High” hypothesis |
| --- | --- | --- | --- |
| Formal sector companies: - Restructuring - Overall upgrading - Specific upgrading | 1425 300 555 570 | 2130 450 840 840 | 2850 600 1125 1125 |
| Informal sector companies | 1425 | 2130 | 2850 |
| Total for companies | 2850 | 4260 | 5700 |
| Technical support institutions | 30 | 30 | 30 |

  - Detailed description of the budget

Taking into account the above hypotheses, the proposed budget scenarios set out the figures for the indicative budget by Programme component and the management, coordination and follow-up costs.

The summaries of respective high, middle and low scenario budgets are reflected in the following tables.

Table 20:  Scenario 1 for the Indicative Budget Breakdown

Table 21:  Scenario 2 for the Indicative Budget Breakdown

Table 22:  Scenario 3 for the Indicative Budget Breakdown

Distribution of funds for enterprises (Component I) should be equal to all Member States in accordance to SADC procedures. The details on the budget breakdowns are provided in Annex IX.

  - Expected impact of the Programme

The Programme of Industrial Upgrading and Modernization is expected to have a significant impact on industrial sector and overall economic performance of SADC countries. More specifically, the Programme will contribute to the region’s development by:

- Strengthening the managerial capacities and marketing skills;

- Improvement of productivity, reactivity and flexibility;

- Mastering and cutting down the production costs;

- Improving the quality and sanitary standards;

- Recovery and re-launch of suspended productive activities;

- Strengthening capacities of the informal sector companies with their subsequent integration into the formal environment;

- Building capacities of the technical support institutions, business advice and consultancy centers;

- Development of exports capacities and imports substitution;

- Creating employment opportunities directly in industries and in agricultural sector and services, indirectly;

- Development and strengthening of the local expertise in order to extend its services to other sectors not directly addressed by the Programme.

Moreover, establishment of the Upgrading Offices, Monitoring Framework insuring management and follow-up of the Programme, and the Investment Platform will allow the SADC Secretariat, as well as the Ministries in charge with industry and trade, to refine their information systems and industrial strategies and policies.

Besides, the Programme is expected to contribute to improving the public-private dialog resulting directly in enhanced promotion of investment, employment and exports.

Finally, the involvement of the financial sector since the kick-off of the Programme, together with mobilized expertise, business-plans designed according to the banks requirements, and “lobbying” as the result of communication within the Programme, - all these factors must materialize in increase of financial resources allotted by the banking sector and diversification of the financial services pattern.

The examples of developing countries which have already implemented the upgrading and modernization programmes (Tunisia, Senegal) allow the estimations of the Programme’s potential impact to the Southern African economies.  The expected impact of the current Programme on the key economic indicators is as follows:

#### Industrial production

Resulting from the lack of dynamism in overall economic activities, the level of production performance in SADC zone remains considerably low. The Upgrading and Modernization Programme will have an immediate impact by increasing efficiency in using available production capacities and resources. Growth of industrial production and increase in turnover of the beneficiary companies by minimum 10-12% per year seem quite probable (+18% per year in Tunisia).

#### Value added

Besides, an increase in production volume due to the growth of industrial production and enhancement of manufacturing processes should result in the net gain in value-added for beneficiary companies.  Thus, the value-added of the beneficiary countries is expected to increase by 12-15% per year during the first 6 years of the Programme implementation.

#### Investments

The expected impact on the global investments flow to SADC economies is between €300 and 600 million subject to selected hypothesis.

As mentioned, the Programme will affect according to the above hypotheses 2850, 4260 or 5700 companies operating in formal and informal sectors of the Southern African region.

The technical assistance and grants for the direct material investments (necessary to upgrade and modernize the companies of formal sector) are estimated on average (between the costs of global and specific approaches) at €47 500 per enterprise. This represents 80% of the immaterial investments costs.

Other assumptions to evaluate the Programme’s impact on the global investments flow are as follows:

- The companies to be involved into the overall Strategic Diagnostics with material and immaterial investments represent 45% of all beneficiary companies.

- The companies to be involved into the restructuring activities with material and immaterial investments represent 10% of all beneficiary companies.

- For these companies, the global investments, including material investments, would represent 4 times allotted grants.

- The share of the companies expected to participate in the specific activities of immaterial investments is 45%.

- The number of informal sector companies participating in this Programme is always equal to the one of formal beneficiary companies.

#### Employment

The flow of the new investments and increase in industrial production will consolidate the existing employment (stabilization of the seasonal staff, switch to the permanent employment, and increase in the placement rate) and also creation of the new places directly in industries and in agricultural sector and services related to industry, indirectly.

Referring to the average number of employees by the enterprise in SADC region, the permanent staff in industrial sector is estimated to be of 50 persons. Having, thus as a scope approximately 600 000-700 000 persons in the region to be affected by the Programme, it is expected that the Programme will contribute to the annual increase in employment at the beneficiary companies by 10%.

The rate of the placement of the young specialist may have the same annual trend of 10%.

#### Exports

The coordinated support activities provided to the technical centers, investment and export promotion agencies and laboratories might assist in achieving the following objectives:

- Increase in the cash flows from exports operations (including intraregional trade) of beneficiary countries by 10% per year.

- 10% of the companies not able to export before the Programme, should start to commercialize abroad.

#### Expertise

The local and regional expertise capacities are expected to be reinforced forming the core of 30 experts by country with the total of 400-450 experts for Southern Africa.

#### Professional education

A considerable improvement in capacities of professional education institutions and training of 3000-4000 artisans, technicians and specialized workers are expected throughout the region.

- MANAGEMENT AND COORDINATION OF THE PROGRAMME

The approach to be applied for Programme management and coordination should be based on:

- the necessary complementarities of the regional and national management mechanisms and structures;

- the Programme presentation to the development partners as complementary to and coherent with the national programmes initiated and carried out in the Member States taking into consideration the national specificities of each country.

The institutional mechanisms will be established in a progressive way ensuring an overall support from the national level to the regional extent. The institutional mechanisms are composed by the steering structures described hereafter.

  - Regional level

      - The SADC Secretariat

This Programme on Upgrading and Modernization of Industries was initiated by SADC Secretariat, which will act according to its regulations and those of its authorized organs in all issues concerning the budget allocation as well as to other legislative or conventional texts. They will be applied to make the necessary arbitrations in using the public funds.

The financial resources brought by international development partners will contribute to backing grants and technical assistance necessary for the upgrading industries and technical support institutions.

The SADC Secretariat will define the conditions of retrocession for the funds provided by development partners and will be responsible for:

- mobilization of financial resources;

- developing Programme funding policy at regional level;

- defining Programme implementation framework : strategic plan, general and specific objectives, intervention framework, etc.;

- establishment of institutions in charge of Programme implementation at regional level;

- maintaining relations with development partners.

The SADC Secretariat will also take charge of the following transverse activities:

- development of information systems;

- development of the consultants database;

- conducting sectoral and other related studies;

- development and management of follow-up and evaluation mechanisms;

- development of human resources (personnel of administrative bodies and private companies, consultants, etc.);

- supporting development of the national capacities.

Diagram 4:

Programme implementation mechanism

      - Regional Steering Committee

The Regional Steering Committee will be composed by representatives of SADC Secretariat, Member States, national and regional banks and private-sector companies.

It will provide assistance to SADC Secretariat in overall coordination and management of the Programme in defining financial strategy for the Programme, carrying out fundraising activities and Programme implementation. The Committee performs as a final decision-making institution/authority.

      - Technical Unit for Upgrading and Modernization

The Technical Unit will be responsible for Programme promotion and communication and management at the national level. It will provide technical support to the national steering committee for upgrading and modernization.

The Unit will seek an effective integration and harmonization of all available technical and human resources (establishment of the regional database of service providers by fields of intervention, etc.) and will carry out all other tasks assigned by the Secretariat, the regional and national steering committees.

The Technical Unit for Upgrading and Modernization could be an autonomous structure or attached to the Ministry of Industry.

      - Technical assistance

The role of the technical assistance would consist in providing institutional and technical support to the Regional Steering Committee and the Technical Unit for Upgrading and Modernization, in particular within the following stages:

- Programme identification and design of its structure;

- preparation of the terms of reference for financial and operational management;

- capacity building activities for the main actors of the Programme;

- identification, recruitment and management of international and national experts for implementation of Programme activities;

- management review of the experts’ activities.

  - National level

      - Member States

The Member States are expected to play a role similar to that of the SADC Secretariat concerning the coordination, management and fund-raising activities. The political goodwill and commitments of the Member States are expected to serve as a key tool in mobilizing other potential actors. The Member States must ensure the transparency and accomplishment of the Programme objectives at the national level.

      - National Steering Committees

Once the Regional Steering Committee makes a decision, the responsibility of its local application is attributed to the National Steering Committees. The latter will be in charge with Programme promotion activities and follow-up of its implementation at the national level.

The National Steering Committees will serve as communication centers channeling information necessary to identify appropriate policies (granting policies implemented at the national level, census of the existing support institutions, consultants to be included to the regional file, technical centers to be promoted, information providing the choice of companies).

      - Offices for Upgrading and Modernization

Based on the experience in some developing countries as Senegal and Mali, and in order to facilitate the mid-term sustainability, it is strongly recommended to provide the Offices for Restructuring and Upgrading with administrative and financial autonomy.

These offices are expected to intervene in the following activities during Phase 1 of the Programme implementation:

- conducting promotional and communication activities at national level;

- identification of potential enterprises according to predefined criteria of eligibility at the regional level;

- review of the diagnostic and Upgrading Programmes;

- ensure the follow-up of Upgrading Programme implementation;

- act as secretary for the National Steering Committee;

- assessment of the Programme’s impact on beneficiary companies.

During Phase 2 of the Programme implementation, the offices will continue to perform as operational centers for management and coordination of implementation of the National Programmes on Upgrading and Modernization.  The personnel of the Offices for Upgrading and Modernization should be highly qualified and possess a significant experience in the industrial sector. It should be recruited on the competitive basis.

Diagram 5 depicts the process of industrial upgrading and modernization.

Diagram 5:

Process of companies’ upgrading

  - Management, Monitoring and Evaluation of the Programme

      - Management of the Programme

At the regional level, the Programme will be implemented by the Technical Unit for Upgrading and Modernization with its office at the SADC Secretariat or at another place determined by the Secretariat. The Unit will be responsible for carrying out all the activities of the Programme and therefore will possess all means necessary to ensure dialogue with the national authorities and monitoring of activities being implemented at the national level. These activities will be managed by the national steering committees appointed on ad-hoc basis for this purpose and under the supervision of the national ministries of industry. Technical assistance to Programme implementation will be entrusted to an Executing Agency.

      - Monitoring and Evaluation

The Regional Steering Committee in collaboration with the Technical Unit for Upgrading and Modernization will ensure the monitoring of Programme implementation. They will meet at least twice a year and report on progress of the Programme. The monitoring and evaluation will be carried out in accordance with rules and practices utilized by UNIDO and donor institutions. The Programme’s schedule includes external monitoring and evaluation missions, a review and evaluation at the end of each phase of the Programme. UNIDO’s Evaluation Group, together with appropriate services of SADC and donor organizations, will participate in the annual reviews and evaluations at the end of each phase of the Programme.

At the country level, the national steering committees will take charge of the coordination and monitoring of the programme’s activities.

Representatives of donor organizations will be invited to attend the main monitoring and evaluation missions related to the Programme implementation. The findings of these missions will be communicated to the SADC Secretariat, UNIDO and donor organizations.

The Regional Steering Committee will elaborate criteria to evaluate results and to measure the progress in achieving the Programme’s objectives. These criteria may be quantitative (evaluation of statistical data) and qualitative (appraisal and perception resulting from a subjective analysis). The detailed criteria will be specified in operational plans.

Evaluation missions should be scheduled and completed in a spirit of collaboration between staff and representatives of all stakeholders and donors, keeping in mind the commitment of the Parties to implement the current Programme in effective and efficient manner. These missions should be scheduled in advance and all procedural issues should be resolved jointly.

      - Reporting

According to the Financing Agreement between the UN and the European Union, UNIDO will submit not later than two months after the start-up of the Programme a draft annual work-plan for approval by the Programme implementation monitoring committee. The first work-plan should incorporate the elements of the preliminary operational work-plan, report on the on-going activities scheduled for the current year and specify their implementation modalities. The annual operational plans will be designed for the calendar year.

UNIDO will also prepare progress reports and two final reports at the end of each phase. These reports will consist of a descriptive section and a financial section, which will cover the entire Programme.

Each report should provide a complete picture of all aspects of Programme implementation over the reporting period. The structure of these reports allows a comparison between the objectives and the scheduled or already implemented activities (including all expenditures carried by UNIDO), the anticipated results and those obtained, as well as the budget of the Programme. The structure of each report should correspond to the Programme’s detailed description and budget breakdown.

The descriptive section of the report will contain the following elements:

- Summary and context of the Programme;

- Activities carried out over the reporting period (directly related to the Programme description and activities scheduled within it);

- Problems encountered and measures applied to overcome them;

- Adjustments made in the Programme implementation;

- Assessment of obtained results using the predetermined success indicators;

- Work-plan for the next period containing a definition of objectives and related performance indicators. If the report is submitted after the end of the reporting period, a new work-plan, albeit provisional, should always be prepared before that date.

The overall operational plan includes a critical analysis of the Programme in all its dimensions - in relation to the organizational evolution and missions of various beneficiaries. This report offers the final organizational structure of the Programme in all its aspects.

The final report will include the above elements (except final bullet) covering the entire Programme implementation period, as well as information on the measures carried out to ensure the visibility of financing by the donor organizations.

  - Assumptions and risks

The SADC RISDP has for an object launching the common free trade zone with all its inherent components, as the total liberalization of the intra-regional trade, development and implementation of the common macroeconomic and sectoral policies, promotion of the investment-friendly business environment. The purpose of the regional strategy is in line with the Millennium Development Goals, the objectives of NEPAD and ACP/EU partnership agreements. The present Programme intervenes in full coherence and synergy with all the above objectives and initiatives.

The success of the current Programme is largely dependent on:

- the political goodwill of the Member States and their commitment to finance the Programme;

- moral and financial commitment of companies’ management to upgrade their productive capacities and thereby to improve their competitiveness;

- commitments of donors to contribute to the Programme funding;

- commitments of the regional and local banking sector institutions to contribute, in particular, to financing the material investments activities;

- commitment to improve business climate and infrastructures.

The major risks are:

- one or more countries do not succeed in contributing to establishment of the operational national institutions for Programme implementation (Upgrading Office, Subcontracting Exchange);

- failure of the financing mechanisms, in particular, for funding the material investment activities, proposed by this Programme.

The above-listed are two important risks for accomplishment of the expected results notably related to the implementation of material and immaterial investments activities.

These assumptions and risks are unlikely due to the strong commitments and interest shown by the SADC Secretariat, the ministries of industry and technical support institutions of the Member States, companies and donors. Various actors of SADC region have committed to contribute to the Programme success closely cooperating with UNIDO.

  - Factors for success

The current Industrial Upgrading and Modernization Programme has been designed considering the development priorities of the SADC regional grouping and its Member States. In fact, this Programme applies the efficiency mechanisms to rationalize activities and expenditures at the regional level, thus aiming at the sustainability of Programme operations and support in their continuous implementation provided by the SADC Secretariat and the SADC Member States.

In addition, the Programme will reinforce the local capacities to ensure sustainability of programme activities. Financing mechanisms will also be introduced to improve accessibility of funding for upgrading activities, and to encourage and motivate enterprises and the private sector to participate in the Programme.

SACU Member States: Botswana, Lesotho, Namibia, South Africa and Swaziland

Based on data collected by UNIDO Programme Formulation Mission

Concerning the informal sector, the major reasons for not registering with any authority is often a lack of knowledge on how to register and the procedures involved.

SADC Press Briefing, 9 March 2004:

Communiqué of Peter Mandelson's Press Office

Idem

In the programme, ‘Upgrading’ refers to immaterial investments activities, while ‘Modernization’ stands for material activities involving providing new equipment. ‘Restructuring’ aims at resolving financial problems.

The global approach of companies upgrading includes global strategic diagnosis, formulation of upgrading programme, and technical assistance in implementing priority activities.

The specific approach consists in diagnosis of the company’s specific problem and assistance in implementing activities, which lead to solve this problem.

Evaluation of European Community Support to Private Sector Development in Third Countries (http://www.oecd.org/dataoecd/32/25/36029538.pdf)

In the UNIDO terminology upgrading is a continuous process aimed at « preparing and adapting the enterprise and its business climate to the demands of free trade and introducing an approach for progress-driven actions, strengthening the enterprise’s strong points while eliminating its weak points ».   Thus, it entails improving enterprise competitiveness in all dimensions such as: production, organization and management systems; quality and certification; training and retraining of human resources; energy saving, marketing and market research; strategic alliances and partnership.

The final evaluation costs are covered by the indicative budget of the current Programme.